## Sheet1
Phase Name* | Phase Owner* | Phase StartDate | Phase EndDate | Phase Weightage(%) | Activity Name* | Activity Owner* | Activity StartDate | Activity EndDate | Activity Weightage | Task ID | Task Name* | Task Category* | Task Owner* | Task StartDate | Task EndDate | Task Weightage(%) | Work Type* | Work Quantity | Work Rate | Work UOM | Task Description | Priority | Predecessor | Dependency Type | Lag Days | Successor
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T1 | Excavation - Task 1 | HVAC Systems | Prasad | 2025-01-01 | 2025-01-09 | 5 | Open | 2311 | 10 | Square Meter | Excavation - Task 1 execution and completion | Medium |  |  |  | T2,T4,T14,T36,T79,T91
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T2 | Excavation - Task 2 | Structural Works | Prasad | 2025-01-16 | 2025-01-21 | 5 | Quantity | 2656 | 10 | Cubic Meter | Excavation - Task 2 execution and completion | High | T1 | FS | 7 | T3,T12
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T3 | Excavation - Task 3 | HVAC Systems | Prasad | 2025-01-21 | 2025-01-26 | 5 | Open | 4072 | 10 | Cubic Meter | Excavation - Task 3 execution and completion | Medium | T2 | FS | 0 | T5,T6,T26,T58,T82
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T4 | Excavation - Task 4 | Structural Works | Prasad | 2025-01-09 | 2025-01-17 | 5 | Quantity | 2773 | 10 | Feet | Excavation - Task 4 execution and completion | Low | T1 | FS | 0 | T19
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T5 | Excavation - Task 5 | Electrical | Prasad | 2025-01-31 | 2025-02-08 | 5 | Open | 3254 | 10 | Kilogram | Excavation - Task 5 execution and completion | Low | T3 | FS | 5 | T30,T86
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T6 | Excavation - Task 6 | Electrical | Prasad | 2025-01-01 | 2025-01-25 | 5 | Quantity | 3228 | 10 | Feet | Excavation - Task 6 execution and completion | Low | T3 | SF | 4 | T17,T18,T34
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T7 | Excavation - Task 7 | Plumbing & Sanitary | Prasad | 2025-01-01 | 2025-01-04 | 5 | Open | 1593 | 10 | Numbers | Excavation - Task 7 execution and completion | Low |  |  |  | T8,T29,T41,T52,T80,T98
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T8 | Excavation - Task 8 | Architectural Works | Prasad | 2025-01-02 | 2025-01-08 | 5 | Quantity | 3827 | 10 | Feet | Excavation - Task 8 execution and completion | High | T7 | FS | -2 | T26,T45
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T9 | Excavation - Task 9 | Finishing | Prasad | 2025-01-01 | 2025-01-03 | 5 | Open | 1619 | 10 | Kilogram | Excavation - Task 9 execution and completion | Low |  |  |  | T11,T12,T15,T21,T64,T86
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T10 | Excavation - Task 10 | Preliminaries & Site Works | Prasad | 2025-01-01 | 2025-01-07 | 5 | Quantity | 1435 | 10 | Square Meter | Excavation - Task 10 execution and completion | High
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T11 | Excavation - Task 11 | Plumbing & Sanitary | Prasad | 2025-01-05 | 2025-01-13 | 5 | Open | 3455 | 10 | Square Meter | Excavation - Task 11 execution and completion | Low | T9 | FS | 2 | T100
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T12 | Excavation - Task 12 | Structural Works | Prasad | 2025-01-16 | 2025-01-20 | 5 | Open | 317 | 10 | Feet | Excavation - Task 12 execution and completion | Medium | T2,T9 | SS,FS | 0,6 | T17,T28,T35,T40,T52
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T13 | Excavation - Task 13 | Electrical | Prasad | 2025-01-01 | 2025-01-06 | 5 | Quantity | 1418 | 10 | Cubic Meter | Excavation - Task 13 execution and completion | High |  |  |  | T108
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T14 | Excavation - Task 14 | Structural Works | Prasad | 2025-01-13 | 2025-01-21 | 5 | Open | 3552 | 10 | Kilogram | Excavation - Task 14 execution and completion | High | T1 | FS | 4 | T17,T23,T59
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T15 | Excavation - Task 15 | Electrical | Prasad | 2025-01-01 | 2025-01-03 | 5 | Quantity | 2280 | 10 | Square Meter | Excavation - Task 15 execution and completion | Medium | T9 | FS | -2 | T21,T42,T91
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T16 | Excavation - Task 16 | Structural Works | Prasad | 2025-01-01 | 2025-01-08 | 5 | Open | 3349 | 10 | Meter | Excavation - Task 16 execution and completion | High |  |  |  | T28,T97
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T17 | Excavation - Task 17 | HVAC Systems | Prasad | 2025-01-24 | 2025-02-03 | 4 | Quantity | 2797 | 10 | Numbers | Excavation - Task 17 execution and completion | Low | T6,T12,T14 | FS,FS,SF | -1,2,-1 | T22,T34
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T18 | Excavation - Task 18 | External Development | Prasad | 2025-01-25 | 2025-01-29 | 4 | Open | 1764 | 10 | Cubic Meter | Excavation - Task 18 execution and completion | Low | T6 | FS | 0 | T63,T77
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T19 | Excavation - Task 19 | Architectural Works | Prasad | 2025-01-19 | 2025-01-24 | 4 | Quantity | 2611 | 10 | Feet | Excavation - Task 19 execution and completion | Medium | T4 | FS | 2 | T23,T57
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T20 | Excavation - Task 20 | Structural Works | Prasad | 2025-01-01 | 2025-01-03 | 4 | Open | 1412 | 10 | Cubic Meter | Excavation - Task 20 execution and completion | Medium |  |  |  | T30
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Excavation | Mahesh | 2025-01-01 | 2025-02-28 | 30 | T21 | Excavation - Task 21 | External Development | Prasad | 2025-01-01 | 2025-01-06 | 4 | Quantity | 326 | 10 | Numbers | Excavation - Task 21 execution and completion | High | T9,T15 | SF,FF | -1,-2 | T54,T74
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T22 | Concrete Works - Task 1 | Plumbing & Sanitary | Prasad | 2025-01-01 | 2025-02-06 | 4 | Open | 4414 | 10 | Meter | Concrete Works - Task 1 execution and completion | Medium | T17 | FF | 3 | T42,T105
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T23 | Concrete Works - Task 2 | Structural Works | Prasad | 2025-01-29 | 2025-01-31 | 4 | Open | 3072 | 10 | Feet | Concrete Works - Task 2 execution and completion | Low | T14,T19 | FS,FS | 4,5 | T24
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T24 | Concrete Works - Task 3 | Plumbing & Sanitary | Prasad | 2025-02-06 | 2025-02-15 | 4 | Quantity | 3606 | 10 | Kilogram | Concrete Works - Task 3 execution and completion | Low | T23 | FS | 6 | T33,T46
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T25 | Concrete Works - Task 4 | Architectural Works | Prasad | 2025-01-01 | 2025-01-07 | 4 | Open | 2716 | 10 | Numbers | Concrete Works - Task 4 execution and completion | Low |  |  |  | T32,T46
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T26 | Concrete Works - Task 5 | Plumbing & Sanitary | Prasad | 2025-01-31 | 2025-02-02 | 4 | Quantity | 3418 | 10 | Feet | Concrete Works - Task 5 execution and completion | High | T3,T8 | FS,FS | 5,6
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T27 | Concrete Works - Task 6 | Finishing | Prasad | 2025-01-01 | 2025-01-06 | 4 | Open | 4599 | 10 | Feet | Concrete Works - Task 6 execution and completion | High |  |  |  | T47,T49,T84
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T28 | Concrete Works - Task 7 | Finishing | Prasad | 2025-01-25 | 2025-01-28 | 4 | Quantity | 2962 | 10 | Numbers | Concrete Works - Task 7 execution and completion | Medium | T12,T16 | FS,FS | 5,1 | T81
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T29 | Concrete Works - Task 8 | Electrical | Prasad | 2025-01-07 | 2025-01-09 | 4 | Open | 1392 | 10 | Feet | Concrete Works - Task 8 execution and completion | Low | T7 | SS | 6 | T47,T67
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T30 | Concrete Works - Task 9 | Structural Works | Prasad | 2025-02-11 | 2025-02-14 | 4 | Quantity | 4204 | 10 | Cubic Meter | Concrete Works - Task 9 execution and completion | High | T20,T5 | FS,FS | 4,3 | T50
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T31 | Concrete Works - Task 10 | Finishing | Prasad | 2025-01-01 | 2025-01-03 | 4 | Open | 2003 | 10 | Numbers | Concrete Works - Task 10 execution and completion | Medium |  |  |  | T37,T50,T51
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T32 | Concrete Works - Task 11 | HVAC Systems | Prasad | 2025-01-01 | 2025-01-06 | 4 | Quantity | 2239 | 10 | Feet | Concrete Works - Task 11 execution and completion | Medium | T25 | SS | -1 | T98
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Mahesh | 2025-01-01 | 2025-02-28 | 40 | T33 | Concrete Works - Task 12 | Structural Works | Prasad | 2025-02-13 | 2025-02-23 | 4 | Open | 551 | 10 | Feet | Concrete Works - Task 12 execution and completion | Medium | T24 | FS | -2 | T36,T50,T66,T107,T117
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T34 | Concrete Works - Task 13 | Structural Works | Prasad | 2025-02-01 | 2025-02-03 | 4 | Open | 2190 | 10 | Meter | Concrete Works - Task 13 execution and completion | Medium | T17,T6 | SS,FS | 2,7 | T125
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T35 | Concrete Works - Task 14 | Architectural Works | Prasad | 2025-01-26 | 2025-01-29 | 4 | Quantity | 2426 | 10 | Square Meter | Concrete Works - Task 14 execution and completion | Medium | T12 | FS | 6
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T36 | Concrete Works - Task 15 | Electrical | Prasad | 2025-01-10 | 2025-02-28 | 4 | Open | 332 | 10 | Feet | Concrete Works - Task 15 execution and completion | Medium | T33,T1 | FF,FS | 5,1
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T37 | Concrete Works - Task 16 | Architectural Works | Prasad | 2025-01-08 | 2025-01-15 | 4 | Quantity | 2614 | 10 | Meter | Concrete Works - Task 16 execution and completion | Low | T31 | SS | 7 | T55,T84
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T38 | Concrete Works - Task 17 | Structural Works | Prasad | 2025-01-01 | 2025-01-04 | 4 | Open | 1800 | 10 | Numbers | Concrete Works - Task 17 execution and completion | Low |  |  |  | T70
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T39 | Concrete Works - Task 18 | Structural Works | Prasad | 2025-01-01 | 2025-01-09 | 4 | Quantity | 928 | 10 | Kilogram | Concrete Works - Task 18 execution and completion | High
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T40 | Concrete Works - Task 19 | Finishing | Prasad | 2025-01-21 | 2025-01-31 | 4 | Open | 2201 | 10 | Square Meter | Concrete Works - Task 19 execution and completion | Low | T12 | FS | 1 | T47,T63
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T41 | Concrete Works - Task 20 | Structural Works | Prasad | 2025-01-01 | 2025-01-05 | 4 | Quantity | 3767 | 10 | Kilogram | Concrete Works - Task 20 execution and completion | Low | T7 | SF | 4
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T42 | Concrete Works - Task 21 | Structural Works | Prasad | 2025-02-09 | 2025-02-18 | 4 | Open | 1103 | 10 | Feet | Concrete Works - Task 21 execution and completion | High | T15,T22 | FS,FS | 4,3 | T44,T52,T67
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T43 | Concrete Works - Task 22 | Architectural Works | Prasad | 2025-01-01 | 2025-01-04 | 4 | Quantity | 396 | 10 | Meter | Concrete Works - Task 22 execution and completion | High
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T44 | Concrete Works - Task 23 | External Development | Prasad | 2025-01-01 | 2025-02-10 | 3 | Open | 4099 | 10 | Kilogram | Concrete Works - Task 23 execution and completion | Low | T42 | SF | 1
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T45 | Concrete Works - Task 24 | Plumbing & Sanitary | Prasad | 2025-01-01 | 2025-01-12 | 3 | Open | 1929 | 10 | Square Meter | Concrete Works - Task 24 execution and completion | Medium | T8 | FF | 4 | T48,T62,T71,T106
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T46 | Concrete Works - Task 25 | Structural Works | Prasad | 2025-02-19 | 2025-02-27 | 3 | Quantity | 468 | 10 | Meter | Concrete Works - Task 25 execution and completion | High | T25,T24 | FS,FS | -1,4
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Concrete Works | Bhargavi | 2025-01-01 | 2025-02-28 | 40 | T47 | Concrete Works - Task 26 | Structural Works | Prasad | 2025-01-30 | 2025-02-05 | 3 | Open | 4166 | 10 | Meter | Concrete Works - Task 26 execution and completion | High | T29,T40,T27 | FS,FS,FS | 0,-1,4 | T61
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T48 | Reinforcement & Formwork - Task 1 | Structural Works | Prasad | 2025-01-13 | 2025-01-15 | 4 | Quantity | 3188 | 10 | Numbers | Reinforcement & Formwork - Task 1 execution and completion | High | T45 | FS | 1 | T53,T65,T76,T118
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T49 | Reinforcement & Formwork - Task 2 | Plumbing & Sanitary | Prasad | 2025-01-07 | 2025-01-10 | 3 | Open | 2083 | 10 | Feet | Reinforcement & Formwork - Task 2 execution and completion | High | T27 | FS | 1 | T131
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T50 | Reinforcement & Formwork - Task 3 | HVAC Systems | Prasad | 2025-02-15 | 2025-02-23 | 3 | Quantity | 1504 | 10 | Feet | Reinforcement & Formwork - Task 3 execution and completion | Medium | T31,T33,T30 | FS,SF,FS | -2,4,1
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T51 | Reinforcement & Formwork - Task 4 | Finishing | Prasad | 2025-01-05 | 2025-01-09 | 3 | Open | 4045 | 10 | Cubic Meter | Reinforcement & Formwork - Task 4 execution and completion | High | T31 | FS | 2 | T100
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T52 | Reinforcement & Formwork - Task 5 | Structural Works | Prasad | 2025-01-25 | 2025-02-08 | 3 | Quantity | 3207 | 10 | Cubic Meter | Reinforcement & Formwork - Task 5 execution and completion | High | T12,T42,T7 | FS,SF,SS | 5,-1,-1 | T72,T103,T151
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T53 | Reinforcement & Formwork - Task 6 | Structural Works | Prasad | 2025-01-18 | 2025-01-21 | 3 | Open | 4182 | 10 | Cubic Meter | Reinforcement & Formwork - Task 6 execution and completion | Low | T48 | FS | 3
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T54 | Reinforcement & Formwork - Task 7 | HVAC Systems | Prasad | 2025-01-04 | 2025-01-13 | 3 | Quantity | 4150 | 10 | Cubic Meter | Reinforcement & Formwork - Task 7 execution and completion | Low | T21 | FS | -2 | T139
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T55 | Reinforcement & Formwork - Task 8 | Electrical | Prasad | 2025-01-21 | 2025-01-27 | 3 | Open | 2968 | 10 | Square Meter | Reinforcement & Formwork - Task 8 execution and completion | Low | T37 | FS | 6 | T120
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T56 | Reinforcement & Formwork - Task 9 | Architectural Works | Prasad | 2025-01-01 | 2025-01-07 | 3 | Open | 1442 | 10 | Kilogram | Reinforcement & Formwork - Task 9 execution and completion | Medium |  |  |  | T102,T109,T114,T126
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T57 | Reinforcement & Formwork - Task 10 | Structural Works | Prasad | 2025-01-30 | 2025-02-08 | 3 | Quantity | 813 | 10 | Kilogram | Reinforcement & Formwork - Task 10 execution and completion | Low | T19 | FS | 6
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T58 | Reinforcement & Formwork - Task 11 | Architectural Works | Prasad | 2025-01-30 | 2025-02-02 | 3 | Open | 3454 | 10 | Kilogram | Reinforcement & Formwork - Task 11 execution and completion | Low | T3 | FS | 4 | T112
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T59 | Reinforcement & Formwork - Task 12 | Preliminaries & Site Works | Prasad | 2025-01-26 | 2025-01-28 | 3 | Quantity | 1298 | 10 | Cubic Meter | Reinforcement & Formwork - Task 12 execution and completion | High | T14 | FS | 5 | T94
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T60 | Reinforcement & Formwork - Task 13 | Electrical | Prasad | 2025-01-01 | 2025-01-11 | 3 | Open | 2063 | 10 | Numbers | Reinforcement & Formwork - Task 13 execution and completion | High
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T61 | Reinforcement & Formwork - Task 14 | Structural Works | Prasad | 2025-02-02 | 2025-02-08 | 3 | Quantity | 1071 | 10 | Numbers | Reinforcement & Formwork - Task 14 execution and completion | Medium | T47 | SS | 3 | T62,T64,T92
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T62 | Reinforcement & Formwork - Task 15 | Structural Works | Prasad | 2025-02-10 | 2025-02-17 | 3 | Open | 3223 | 10 | Cubic Meter | Reinforcement & Formwork - Task 15 execution and completion | Medium | T61,T45 | FS,FS | 2,-1 | T86
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T63 | Reinforcement & Formwork - Task 16 | Architectural Works | Prasad | 2025-02-04 | 2025-02-07 | 3 | Quantity | 1334 | 10 | Kilogram | Reinforcement & Formwork - Task 16 execution and completion | Low | T18,T40 | FS,FS | 6,1 | T117,T122
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T64 | Reinforcement & Formwork - Task 17 | Structural Works | Prasad | 2025-02-09 | 2025-02-12 | 3 | Open | 1148 | 10 | Numbers | Reinforcement & Formwork - Task 17 execution and completion | High | T9,T61 | FF,FS | 1,1 | T66
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T65 | Reinforcement & Formwork - Task 18 | HVAC Systems | Prasad | 2025-01-16 | 2025-01-24 | 3 | Quantity | 883 | 10 | Numbers | Reinforcement & Formwork - Task 18 execution and completion | High | T48 | FS | 1 | T87,T146
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T66 | Reinforcement & Formwork - Task 19 | Electrical | Prasad | 2025-02-28 | 2025-02-28 | 3 | Open | 3954 | 10 | Numbers | Reinforcement & Formwork - Task 19 execution and completion | High | T33,T64 | FS,FS | 5,7 | T141
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T67 | Reinforcement & Formwork - Task 20 | Structural Works | Prasad | 2025-02-20 | 2025-02-26 | 3 | Open | 3129 | 10 | Numbers | Reinforcement & Formwork - Task 20 execution and completion | Medium | T42,T29 | FS,SF | 2,-2
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T68 | Reinforcement & Formwork - Task 21 | Plumbing & Sanitary | Prasad | 2025-01-01 | 2025-01-11 | 3 | Quantity | 1018 | 10 | Meter | Reinforcement & Formwork - Task 21 execution and completion | High |  |  |  | T124
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T69 | Reinforcement & Formwork - Task 22 | Electrical | Prasad | 2025-01-01 | 2025-01-05 | 3 | Open | 2499 | 10 | Feet | Reinforcement & Formwork - Task 22 execution and completion | Medium |  |  |  | T89,T140,T158
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T70 | Reinforcement & Formwork - Task 23 | Electrical | Prasad | 2025-01-10 | 2025-01-12 | 3 | Quantity | 1887 | 10 | Square Meter | Reinforcement & Formwork - Task 23 execution and completion | High | T38 | FS | 6 | T71,T88
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T71 | Reinforcement & Formwork - Task 24 | Structural Works | Prasad | 2025-01-10 | 2025-01-17 | 3 | Open | 4996 | 10 | Square Meter | Reinforcement & Formwork - Task 24 execution and completion | Low | T70,T45 | FS,SS | -2,5
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T72 | Reinforcement & Formwork - Task 25 | Architectural Works | Prasad | 2025-01-23 | 2025-01-28 | 3 | Quantity | 1516 | 10 | Square Meter | Reinforcement & Formwork - Task 25 execution and completion | Low | T52 | SS | -2 | T124
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T73 | Reinforcement & Formwork - Task 26 | Preliminaries & Site Works | Prasad | 2025-01-01 | 2025-01-05 | 3 | Open | 3927 | 10 | Kilogram | Reinforcement & Formwork - Task 26 execution and completion | Low
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T74 | Reinforcement & Formwork - Task 27 | Finishing | Prasad | 2025-01-05 | 2025-01-14 | 3 | Quantity | 1507 | 10 | Numbers | Reinforcement & Formwork - Task 27 execution and completion | High | T21 | FS | -1
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T75 | Reinforcement & Formwork - Task 28 | Plumbing & Sanitary | Prasad | 2025-01-01 | 2025-01-08 | 3 | Open | 2245 | 10 | Meter | Reinforcement & Formwork - Task 28 execution and completion | Medium |  |  |  | T98,T118,T164
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T76 | Reinforcement & Formwork - Task 29 | Structural Works | Prasad | 2025-01-21 | 2025-01-27 | 3 | Quantity | 3941 | 10 | Cubic Meter | Reinforcement & Formwork - Task 29 execution and completion | Low | T48 | FS | 6 | T84
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T77 | Reinforcement & Formwork - Task 30 | Structural Works | Vamsi | 2025-02-05 | 2025-02-15 | 3 | Open | 3554 | 10 | Numbers | Reinforcement & Formwork - Task 30 execution and completion | High | T18 | FS | 7
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T78 | Reinforcement & Formwork - Task 31 | Electrical | Vamsi | 2025-01-01 | 2025-01-07 | 3 | Open | 3521 | 10 | Kilogram | Reinforcement & Formwork - Task 31 execution and completion | High |  |  |  | T87,T88
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T79 | Reinforcement & Formwork - Task 32 | HVAC Systems | Vamsi | 2025-01-15 | 2025-01-18 | 3 | Quantity | 3274 | 10 | Numbers | Reinforcement & Formwork - Task 32 execution and completion | Medium | T1 | FS | 6 | T118
Foundation | Bharath | 2025-01-01 | 2025-02-28 | 15 | Reinforcement & Formwork | Bhargavi | 2025-01-01 | 2025-02-28 | 30 | T80 | Reinforcement & Formwork - Task 33 | External Development | Vamsi | 2025-01-01 | 2025-01-04 | 3 | Open | 2179 | 10 | Feet | Reinforcement & Formwork - Task 33 execution and completion | Low | T7 | SF | 1
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T81 | Frame Structure - Task 1 | Structural Works | Vamsi | 2025-03-01 | 2025-03-07 | 4 | Quantity | 916 | 10 | Feet | Frame Structure - Task 1 execution and completion | Low | T28 | FS | 0
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T82 | Frame Structure - Task 2 | Preliminaries & Site Works | Vamsi | 2025-03-01 | 2025-03-07 | 4 | Open | 1595 | 10 | Cubic Meter | Frame Structure - Task 2 execution and completion | High | T3 | FF | 3 | T153
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T83 | Frame Structure - Task 3 | Structural Works | Vamsi | 2025-03-01 | 2025-03-06 | 4 | Quantity | 1487 | 10 | Numbers | Frame Structure - Task 3 execution and completion | High |  |  |  | T153
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T84 | Frame Structure - Task 4 | HVAC Systems | Vamsi | 2025-03-01 | 2025-03-09 | 4 | Open | 919 | 10 | Kilogram | Frame Structure - Task 4 execution and completion | High | T76,T27,T37 | FS,FS,FS | 6,1,4 | T160
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T85 | Frame Structure - Task 5 | HVAC Systems | Vamsi | 2025-03-01 | 2025-03-06 | 4 | Quantity | 4838 | 10 | Kilogram | Frame Structure - Task 5 execution and completion | Low
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T86 | Frame Structure - Task 6 | HVAC Systems | Vamsi | 2025-03-01 | 2025-03-04 | 4 | Open | 4972 | 10 | Cubic Meter | Frame Structure - Task 6 execution and completion | Low | T62,T5,T9 | FS,FS,FS | 3,5,5
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T87 | Frame Structure - Task 7 | Architectural Works | Vamsi | 2025-03-01 | 2025-03-11 | 4 | Quantity | 4982 | 10 | Meter | Frame Structure - Task 7 execution and completion | Low | T78,T65 | FS,SF | -1,2
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T88 | Frame Structure - Task 8 | Plumbing & Sanitary | Vamsi | 2025-03-01 | 2025-03-10 | 4 | Open | 3686 | 10 | Square Meter | Frame Structure - Task 8 execution and completion | High | T70,T78 | FS,FS | 6,4 | T167
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T89 | Frame Structure - Task 9 | External Development | Vamsi | 2025-03-01 | 2025-03-09 | 4 | Open | 3102 | 10 | Feet | Frame Structure - Task 9 execution and completion | High | T69 | FS | 6 | T104,T174
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T90 | Frame Structure - Task 10 | Structural Works | Vamsi | 2025-03-01 | 2025-03-08 | 4 | Quantity | 1486 | 10 | Kilogram | Frame Structure - Task 10 execution and completion | Medium |  |  |  | T109
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T91 | Frame Structure - Task 11 | Electrical | Vamsi | 2025-03-01 | 2025-03-10 | 4 | Open | 2143 | 10 | Feet | Frame Structure - Task 11 execution and completion | High | T15,T1 | FS,SF | 1,-2
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T92 | Frame Structure - Task 12 | Plumbing & Sanitary | Vamsi | 2025-03-01 | 2025-03-06 | 4 | Quantity | 4501 | 10 | Square Meter | Frame Structure - Task 12 execution and completion | High | T61 | FS | 2 | T122,T129,T151
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T93 | Frame Structure - Task 13 | Structural Works | Vamsi | 2025-03-01 | 2025-03-10 | 4 | Open | 770 | 10 | Kilogram | Frame Structure - Task 13 execution and completion | Medium |  |  |  | T125,T151,T192
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T94 | Frame Structure - Task 14 | Architectural Works | Vamsi | 2025-03-01 | 2025-03-08 | 4 | Quantity | 3392 | 10 | Meter | Frame Structure - Task 14 execution and completion | High | T59 | FS | -1 | T96
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T95 | Frame Structure - Task 15 | HVAC Systems | Vamsi | 2025-03-01 | 2025-03-09 | 4 | Open | 2575 | 10 | Meter | Frame Structure - Task 15 execution and completion | High |  |  |  | T142,T163
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T96 | Frame Structure - Task 16 | HVAC Systems | Prasad | 2025-03-13 | 2025-03-17 | 4 | Quantity | 2864 | 10 | Kilogram | Frame Structure - Task 16 execution and completion | Low | T94 | FS | 5 | T127,T172
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T97 | Frame Structure - Task 17 | Plumbing & Sanitary | Prasad | 2025-03-01 | 2025-03-10 | 3 | Open | 4931 | 10 | Kilogram | Frame Structure - Task 17 execution and completion | Low | T16 | FS | 3
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T98 | Frame Structure - Task 18 | Preliminaries & Site Works | Prasad | 2025-03-01 | 2025-03-03 | 3 | Quantity | 2067 | 10 | Square Meter | Frame Structure - Task 18 execution and completion | Medium | T7,T32,T75 | FS,FS,FS | 5,0,7 | T116
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T99 | Frame Structure - Task 19 | Structural Works | Prasad | 2025-03-01 | 2025-03-08 | 3 | Open | 1817 | 10 | Meter | Frame Structure - Task 19 execution and completion | Medium
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T100 | Frame Structure - Task 20 | Structural Works | Prasad | 2025-03-01 | 2025-03-07 | 3 | Open | 305 | 10 | Feet | Frame Structure - Task 20 execution and completion | High | T11,T51 | FS,SS | 3,6 | T123,T124
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T101 | Frame Structure - Task 21 | HVAC Systems | Prasad | 2025-03-01 | 2025-03-06 | 3 | Quantity | 1229 | 10 | Cubic Meter | Frame Structure - Task 21 execution and completion | Medium
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T102 | Frame Structure - Task 22 | External Development | Prasad | 2025-03-01 | 2025-03-09 | 3 | Open | 2170 | 10 | Meter | Frame Structure - Task 22 execution and completion | Low | T56 | FS | 3
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T103 | Frame Structure - Task 23 | Preliminaries & Site Works | Prasad | 2025-03-01 | 2025-03-07 | 3 | Quantity | 2489 | 10 | Numbers | Frame Structure - Task 23 execution and completion | Medium | T52 | FS | 1 | T143,T176
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T104 | Frame Structure - Task 24 | Electrical | Prasad | 2025-03-15 | 2025-03-23 | 3 | Open | 336 | 10 | Meter | Frame Structure - Task 24 execution and completion | High | T89 | FS | 6 | T144,T150
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T105 | Frame Structure - Task 25 | External Development | Prasad | 2025-03-01 | 2025-03-05 | 3 | Quantity | 927 | 10 | Kilogram | Frame Structure - Task 25 execution and completion | High | T22 | FS | 4 | T128
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T106 | Frame Structure - Task 26 | External Development | Prasad | 2025-03-01 | 2025-03-09 | 3 | Open | 1214 | 10 | Square Meter | Frame Structure - Task 26 execution and completion | Low | T45 | SF | 6 | T128
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T107 | Frame Structure - Task 27 | Architectural Works | Prasad | 2025-03-01 | 2025-03-06 | 3 | Quantity | 2391 | 10 | Feet | Frame Structure - Task 27 execution and completion | Low | T33 | FS | -1 | T127
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Frame Structure | Bhargavi | 2025-03-01 | 2025-12-31 | 40 | T108 | Frame Structure - Task 28 | Finishing | Prasad | 2025-03-01 | 2025-03-08 | 3 | Open | 2895 | 10 | Cubic Meter | Frame Structure - Task 28 execution and completion | High | T13 | SS | -2 | T130
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T109 | Masonry Works - Task 1 | HVAC Systems | Prasad | 2025-03-08 | 2025-03-10 | 5 | Quantity | 4268 | 10 | Numbers | Masonry Works - Task 1 execution and completion | High | T56,T90 | FS,FS | -2,0 | T138
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T110 | Masonry Works - Task 2 | Architectural Works | Prasad | 2025-03-01 | 2025-03-04 | 5 | Open | 4509 | 10 | Kilogram | Masonry Works - Task 2 execution and completion | Low
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T111 | Masonry Works - Task 3 | Structural Works | Prasad | 2025-03-01 | 2025-03-04 | 5 | Open | 3003 | 10 | Cubic Meter | Masonry Works - Task 3 execution and completion | Low
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T112 | Masonry Works - Task 4 | External Development | Prasad | 2025-03-01 | 2025-03-08 | 5 | Quantity | 618 | 10 | Kilogram | Masonry Works - Task 4 execution and completion | High | T58 | FS | -1 | T191
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T113 | Masonry Works - Task 5 | Finishing | Prasad | 2025-03-01 | 2025-03-03 | 5 | Open | 1612 | 10 | Numbers | Masonry Works - Task 5 execution and completion | High |  |  |  | T156,T162
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T114 | Masonry Works - Task 6 | Finishing | Prasad | 2025-03-01 | 2025-03-08 | 5 | Quantity | 2661 | 10 | Cubic Meter | Masonry Works - Task 6 execution and completion | Low | T56 | FF | 2 | T137
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T115 | Masonry Works - Task 7 | Structural Works | Prasad | 2025-03-01 | 2025-03-03 | 5 | Open | 3564 | 10 | Kilogram | Masonry Works - Task 7 execution and completion | Medium |  |  |  | T149,T152
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T116 | Masonry Works - Task 8 | Plumbing & Sanitary | Prasad | 2025-03-08 | 2025-03-18 | 5 | Quantity | 2533 | 10 | Square Meter | Masonry Works - Task 8 execution and completion | High | T98 | FS | 5 | T164
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T117 | Masonry Works - Task 9 | Structural Works | Prasad | 2025-03-01 | 2025-03-08 | 4 | Open | 640 | 10 | Feet | Masonry Works - Task 9 execution and completion | Medium | T63,T33 | SF,SF | -2,2 | T212
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T118 | Masonry Works - Task 10 | External Development | Prasad | 2025-03-01 | 2025-03-09 | 4 | Quantity | 4733 | 10 | Numbers | Masonry Works - Task 10 execution and completion | Low | T48,T75,T79 | FS,SF,FS | -1,1,3 | T123,T152,T154,T159
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T119 | Masonry Works - Task 11 | Architectural Works | Prasad | 2025-03-01 | 2025-03-03 | 4 | Open | 330 | 10 | Meter | Masonry Works - Task 11 execution and completion | Medium |  |  |  | T136,T160,T201
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T120 | Masonry Works - Task 12 | Structural Works | Prasad | 2025-03-01 | 2025-03-07 | 4 | Quantity | 1662 | 10 | Square Meter | Masonry Works - Task 12 execution and completion | Medium | T55 | FS | -2 | T214
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T121 | Masonry Works - Task 13 | External Development | Prasad | 2025-03-01 | 2025-03-05 | 4 | Open | 1156 | 10 | Numbers | Masonry Works - Task 13 execution and completion | High |  |  |  | T173
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T122 | Masonry Works - Task 14 | Architectural Works | Prasad | 2025-03-06 | 2025-03-08 | 4 | Open | 4069 | 10 | Numbers | Masonry Works - Task 14 execution and completion | High | T63,T92 | FS,FS | 2,0 | T128,T155
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T123 | Masonry Works - Task 15 | External Development | Prasad | 2025-03-11 | 2025-03-14 | 4 | Quantity | 957 | 10 | Kilogram | Masonry Works - Task 15 execution and completion | Medium | T100,T118 | FS,FS | 4,-1 | T160
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T124 | Masonry Works - Task 16 | Preliminaries & Site Works | Prasad | 2025-03-01 | 2025-03-07 | 4 | Open | 4899 | 10 | Kilogram | Masonry Works - Task 16 execution and completion | Low | T72,T68,T100 | SS,FS,SF | 2,3,1
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T125 | Masonry Works - Task 17 | Electrical | Prasad | 2025-03-11 | 2025-03-21 | 4 | Quantity | 323 | 10 | Cubic Meter | Masonry Works - Task 17 execution and completion | High | T34,T93 | SS,FS | 2,1 | T139,T179
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T126 | Masonry Works - Task 18 | Structural Works | Prasad | 2025-03-01 | 2025-03-03 | 4 | Open | 4910 | 10 | Kilogram | Masonry Works - Task 18 execution and completion | High | T56 | FS | 7 | T165,T178,T227
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T127 | Masonry Works - Task 19 | HVAC Systems | Prasad | 2025-03-20 | 2025-03-30 | 4 | Quantity | 1011 | 10 | Cubic Meter | Masonry Works - Task 19 execution and completion | Medium | T96,T107 | FS,FS | 3,3
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T128 | Masonry Works - Task 20 | Finishing | Prasad | 2025-03-12 | 2025-03-22 | 4 | Open | 4314 | 10 | Feet | Masonry Works - Task 20 execution and completion | High | T122,T105,T106 | FS,FS,SS | 4,3,1
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T129 | Masonry Works - Task 21 | Finishing | Prasad | 2025-03-09 | 2025-03-19 | 4 | Quantity | 1885 | 10 | Square Meter | Masonry Works - Task 21 execution and completion | Medium | T92 | FS | 3 | T149,T185
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T130 | Masonry Works - Task 22 | Plumbing & Sanitary | Prasad | 2025-03-01 | 2025-03-06 | 4 | Open | 594 | 10 | Numbers | Masonry Works - Task 22 execution and completion | Low | T108 | SF | 2 | T199
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Masonry Works | Bhargavi | 2025-03-01 | 2025-12-31 | 35 | T131 | Masonry Works - Task 23 | Electrical | Prasad | 2025-03-01 | 2025-03-08 | 4 | Quantity | 2720 | 10 | Kilogram | Masonry Works - Task 23 execution and completion | Low | T49 | FS | 5 | T213
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T132 | Roofing - Task 1 | External Development | Prasad | 2025-03-01 | 2025-03-08 | 4 | Open | 4013 | 10 | Meter | Roofing - Task 1 execution and completion | High
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T133 | Roofing - Task 2 | Electrical | Prasad | 2025-03-01 | 2025-03-05 | 3 | Open | 2054 | 10 | Square Meter | Roofing - Task 2 execution and completion | High |  |  |  | T190
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T134 | Roofing - Task 3 | Structural Works | Prasad | 2025-03-01 | 2025-03-05 | 3 | Quantity | 3413 | 10 | Numbers | Roofing - Task 3 execution and completion | Medium |  |  |  | T140,T226
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T135 | Roofing - Task 4 | Preliminaries & Site Works | Prasad | 2025-03-01 | 2025-03-10 | 3 | Open | 3880 | 10 | Kilogram | Roofing - Task 4 execution and completion | High
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T136 | Roofing - Task 5 | HVAC Systems | Prasad | 2025-03-05 | 2025-03-15 | 3 | Quantity | 1871 | 10 | Kilogram | Roofing - Task 5 execution and completion | Medium | T119 | FS | 2
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T137 | Roofing - Task 6 | Plumbing & Sanitary | Prasad | 2025-03-08 | 2025-03-18 | 3 | Open | 3175 | 10 | Square Meter | Roofing - Task 6 execution and completion | High | T114 | FS | 0 | T138
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T138 | Roofing - Task 7 | Structural Works | Prasad | 2025-03-16 | 2025-03-19 | 3 | Quantity | 557 | 10 | Square Meter | Roofing - Task 7 execution and completion | Medium | T109,T137 | FF,FS | 6,-2 | T179,T198
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Bhargavi | 2025-03-01 | 2025-12-31 | 25 | T139 | Roofing - Task 8 | Structural Works | Prasad | 2025-03-27 | 2025-03-30 | 3 | Open | 1513 | 10 | Feet | Roofing - Task 8 execution and completion | Medium | T54,T125 | FS,FS | -1,6
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T140 | Roofing - Task 9 | Preliminaries & Site Works | Prasad | 2025-03-09 | 2025-03-17 | 3 | Quantity | 1665 | 10 | Numbers | Roofing - Task 9 execution and completion | Low | T134,T69 | FS,FS | 4,3 | T162,T179,T229
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T141 | Roofing - Task 10 | Structural Works | Prasad | 2025-03-06 | 2025-03-12 | 3 | Open | 3123 | 10 | Feet | Roofing - Task 10 execution and completion | Medium | T66 | FS | -2 | T149,T156,T186,T195
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T142 | Roofing - Task 11 | Structural Works | Prasad | 2025-03-15 | 2025-03-25 | 3 | Quantity | 1967 | 10 | Meter | Roofing - Task 11 execution and completion | Low | T95 | FS | 6 | T182
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T143 | Roofing - Task 12 | HVAC Systems | Prasad | 2025-03-05 | 2025-03-11 | 3 | Open | 2857 | 10 | Square Meter | Roofing - Task 12 execution and completion | High | T103 | FS | -2 | T169,T183,T194
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T144 | Roofing - Task 13 | Plumbing & Sanitary | Prasad | 2025-03-01 | 2025-03-13 | 3 | Open | 1924 | 10 | Square Meter | Roofing - Task 13 execution and completion | Medium | T104 | SF | -2 | T215,T230
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T145 | Roofing - Task 14 | Structural Works | Prasad | 2025-03-01 | 2025-03-10 | 3 | Quantity | 2971 | 10 | Square Meter | Roofing - Task 14 execution and completion | High |  |  |  | T163
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T146 | Roofing - Task 15 | Preliminaries & Site Works | Prasad | 2025-03-01 | 2025-03-11 | 3 | Open | 3368 | 10 | Kilogram | Roofing - Task 15 execution and completion | High | T65 | FS | 0
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T147 | Roofing - Task 16 | Structural Works | Prasad | 2025-03-01 | 2025-03-11 | 3 | Quantity | 3426 | 10 | Meter | Roofing - Task 16 execution and completion | High |  |  |  | T226
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T148 | Roofing - Task 17 | HVAC Systems | Vamsi | 2025-03-01 | 2025-03-05 | 3 | Open | 4547 | 10 | Square Meter | Roofing - Task 17 execution and completion | Medium
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T149 | Roofing - Task 18 | Preliminaries & Site Works | Vamsi | 2025-03-26 | 2025-04-04 | 3 | Quantity | 2631 | 10 | Numbers | Roofing - Task 18 execution and completion | Medium | T141,T115,T129 | SF,SF,FS | 6,5,7 | T221
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T150 | Roofing - Task 19 | Finishing | Vamsi | 2025-03-22 | 2025-04-01 | 3 | Open | 2147 | 10 | Cubic Meter | Roofing - Task 19 execution and completion | Low | T104 | FS | -1 | T181,T193
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T151 | Roofing - Task 20 | Structural Works | Vamsi | 2025-03-01 | 2025-03-09 | 3 | Quantity | 142 | 10 | Kilogram | Roofing - Task 20 execution and completion | Medium | T93,T92,T52 | SF,SF,FS | 4,6,6 | T183,T231,T242
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T152 | Roofing - Task 21 | Finishing | Vamsi | 2025-03-16 | 2025-03-18 | 3 | Open | 734 | 10 | Feet | Roofing - Task 21 execution and completion | Medium | T118,T115 | FS,FS | 7,6 | T210
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T153 | Roofing - Task 22 | Finishing | Vamsi | 2025-03-08 | 2025-03-15 | 3 | Quantity | 4371 | 10 | Meter | Roofing - Task 22 execution and completion | Medium | T82,T83 | FS,FS | 1,-2
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T154 | Roofing - Task 23 | Finishing | Vamsi | 2025-03-01 | 2025-03-13 | 3 | Open | 2698 | 10 | Numbers | Roofing - Task 23 execution and completion | Low | T118 | FF | 4
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T155 | Roofing - Task 24 | Structural Works | Vamsi | 2025-03-08 | 2025-03-12 | 3 | Open | 974 | 10 | Numbers | Roofing - Task 24 execution and completion | High | T122 | FS | 0 | T162,T168,T176
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T156 | Roofing - Task 25 | Structural Works | Vamsi | 2025-03-17 | 2025-03-19 | 3 | Quantity | 1824 | 10 | Feet | Roofing - Task 25 execution and completion | High | T141,T113 | FS,FS | 5,3 | T197
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T157 | Roofing - Task 26 | Structural Works | Vamsi | 2025-03-01 | 2025-03-11 | 3 | Open | 2995 | 10 | Numbers | Roofing - Task 26 execution and completion | Medium |  |  |  | T195
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T158 | Roofing - Task 27 | Structural Works | Vamsi | 2025-03-01 | 2025-03-06 | 3 | Quantity | 3442 | 10 | Kilogram | Roofing - Task 27 execution and completion | Low | T69 | FS | 7
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T159 | Roofing - Task 28 | External Development | Vamsi | 2025-03-11 | 2025-03-16 | 3 | Open | 358 | 10 | Feet | Roofing - Task 28 execution and completion | Low | T118 | FS | 2 | T206
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T160 | Roofing - Task 29 | Structural Works | Vamsi | 2025-03-16 | 2025-03-21 | 3 | Quantity | 1070 | 10 | Cubic Meter | Roofing - Task 29 execution and completion | Medium | T119,T123,T84 | FF,SS,FF | 5,5,0 | T164
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T161 | Roofing - Task 30 | Finishing | Vamsi | 2025-03-01 | 2025-03-03 | 3 | Open | 3102 | 10 | Feet | Roofing - Task 30 execution and completion | High |  |  |  | T198,T202,T203,T245
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T162 | Roofing - Task 31 | Architectural Works | Vamsi | 2025-03-19 | 2025-03-23 | 3 | Quantity | 4661 | 10 | Numbers | Roofing - Task 31 execution and completion | Low | T155,T140,T113 | FS,FS,FS | 0,2,3
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T163 | Roofing - Task 32 | Architectural Works | Vamsi | 2025-03-11 | 2025-03-18 | 3 | Open | 332 | 10 | Kilogram | Roofing - Task 32 execution and completion | Medium | T145,T95 | FS,FS | 1,2 | T189,T198,T214,T248
Superstructure | Bharath | 2025-03-01 | 2025-12-31 | 35 | Roofing | Mahesh | 2025-03-01 | 2025-12-31 | 25 | T164 | Roofing - Task 33 | External Development | Vamsi | 2025-03-24 | 2025-03-31 | 3 | Quantity | 3333 | 10 | Square Meter | Roofing - Task 33 execution and completion | High | T75,T116,T160 | FS,FS,FS | 7,6,1 | T229,T242
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Mahesh | 2026-01-01 | 2026-06-30 | 35 | T165 | Electrical - Task 1 | Structural Works | Vamsi | 2026-01-01 | 2026-01-08 | 4 | Open | 2778 | 10 | Square Meter | Electrical - Task 1 execution and completion | High | T126 | SF | -2 | T194,T218,T223
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Mahesh | 2026-01-01 | 2026-06-30 | 35 | T166 | Electrical - Task 2 | Structural Works | Prasad | 2026-01-01 | 2026-01-09 | 4 | Open | 3302 | 10 | Cubic Meter | Electrical - Task 2 execution and completion | High
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Mahesh | 2026-01-01 | 2026-06-30 | 35 | T167 | Electrical - Task 3 | Structural Works | Prasad | 2026-01-01 | 2026-01-03 | 4 | Quantity | 192 | 10 | Numbers | Electrical - Task 3 execution and completion | Low | T88 | FS | 0
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Mahesh | 2026-01-01 | 2026-06-30 | 35 | T168 | Electrical - Task 4 | Electrical | Prasad | 2026-01-01 | 2026-01-07 | 4 | Open | 2026 | 10 | Feet | Electrical - Task 4 execution and completion | Low | T155 | FS | 4 | T212
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Mahesh | 2026-01-01 | 2026-06-30 | 35 | T169 | Electrical - Task 5 | Electrical | Prasad | 2026-01-01 | 2026-01-11 | 4 | Quantity | 959 | 10 | Meter | Electrical - Task 5 execution and completion | Low | T143 | FS | 4 | T247
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T170 | Electrical - Task 6 | Electrical | Prasad | 2026-01-01 | 2026-01-11 | 4 | Open | 3600 | 10 | Square Meter | Electrical - Task 6 execution and completion | High |  |  |  | T242
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T171 | Electrical - Task 7 | Structural Works | Prasad | 2026-01-01 | 2026-01-03 | 4 | Quantity | 445 | 10 | Numbers | Electrical - Task 7 execution and completion | High |  |  |  | T206,T212,T252
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T172 | Electrical - Task 8 | Electrical | Prasad | 2026-01-01 | 2026-01-05 | 4 | Open | 1726 | 10 | Kilogram | Electrical - Task 8 execution and completion | High | T96 | SS | 5 | T205
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T173 | Electrical - Task 9 | Electrical | Prasad | 2026-01-01 | 2026-01-09 | 4 | Quantity | 2764 | 10 | Square Meter | Electrical - Task 9 execution and completion | High | T121 | FS | 3
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T174 | Electrical - Task 10 | Electrical | Prasad | 2026-01-01 | 2026-01-06 | 4 | Open | 1790 | 10 | Kilogram | Electrical - Task 10 execution and completion | Low | T89 | FS | 3 | T216
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T175 | Electrical - Task 11 | Architectural Works | Prasad | 2026-01-01 | 2026-01-05 | 4 | Quantity | 343 | 10 | Numbers | Electrical - Task 11 execution and completion | Low |  |  |  | T176,T224
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T176 | Electrical - Task 12 | Finishing | Prasad | 2026-01-10 | 2026-01-17 | 4 | Open | 1954 | 10 | Kilogram | Electrical - Task 12 execution and completion | High | T175,T103,T155 | FS,FS,FS | 5,-1,7
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T177 | Electrical - Task 13 | External Development | Prasad | 2026-01-01 | 2026-01-03 | 4 | Open | 2216 | 10 | Feet | Electrical - Task 13 execution and completion | Medium |  |  |  | T219
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T178 | Electrical - Task 14 | Electrical | Prasad | 2026-01-01 | 2026-01-08 | 3 | Quantity | 1149 | 10 | Kilogram | Electrical - Task 14 execution and completion | Low | T126 | SS | 5 | T186
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T179 | Electrical - Task 15 | Structural Works | Prasad | 2026-01-01 | 2026-01-11 | 3 | Open | 4684 | 10 | Cubic Meter | Electrical - Task 15 execution and completion | High | T140,T138,T125 | FS,FS,FS | 6,2,6 | T262
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T180 | Electrical - Task 16 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-08 | 3 | Quantity | 3291 | 10 | Numbers | Electrical - Task 16 execution and completion | High |  |  |  | T202,T255,T283
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T181 | Electrical - Task 17 | Structural Works | Prasad | 2026-01-01 | 2026-01-09 | 3 | Open | 3311 | 10 | Feet | Electrical - Task 17 execution and completion | Medium | T150 | FS | 4
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T182 | Electrical - Task 18 | Structural Works | Prasad | 2026-01-01 | 2026-01-06 | 3 | Quantity | 216 | 10 | Square Meter | Electrical - Task 18 execution and completion | Medium | T142 | FS | 0 | T231,T265,T281
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T183 | Electrical - Task 19 | Finishing | Prasad | 2026-01-01 | 2026-01-03 | 3 | Open | 1886 | 10 | Square Meter | Electrical - Task 19 execution and completion | Medium | T143,T151 | FS,SF | 2,3 | T287
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T184 | Electrical - Task 20 | Plumbing & Sanitary | Prasad | 2026-01-01 | 2026-01-06 | 3 | Quantity | 13 | 10 | Numbers | Electrical - Task 20 execution and completion | Medium |  |  |  | T211,T284
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T185 | Electrical - Task 21 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-11 | 3 | Open | 4668 | 10 | Feet | Electrical - Task 21 execution and completion | Low | T129 | SS | 0 | T194,T229,T267
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T186 | Electrical - Task 22 | Structural Works | Prasad | 2026-01-13 | 2026-01-22 | 3 | Quantity | 52 | 10 | Square Meter | Electrical - Task 22 execution and completion | Low | T178,T141 | FS,FS | 5,0
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T187 | Electrical - Task 23 | Plumbing & Sanitary | Prasad | 2026-01-01 | 2026-01-06 | 3 | Open | 746 | 10 | Numbers | Electrical - Task 23 execution and completion | Low |  |  |  | T286
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T188 | Electrical - Task 24 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-11 | 3 | Open | 4942 | 10 | Kilogram | Electrical - Task 24 execution and completion | High |  |  |  | T277
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T189 | Electrical - Task 25 | Structural Works | Prasad | 2026-01-01 | 2026-01-08 | 3 | Quantity | 4704 | 10 | Square Meter | Electrical - Task 25 execution and completion | High | T163 | FS | 7
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T190 | Electrical - Task 26 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-10 | 3 | Open | 2101 | 10 | Cubic Meter | Electrical - Task 26 execution and completion | High | T133 | FF | 7 | T204,T238
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T191 | Electrical - Task 27 | Structural Works | Prasad | 2026-01-01 | 2026-01-06 | 3 | Quantity | 2640 | 10 | Numbers | Electrical - Task 27 execution and completion | Medium | T112 | FS | -1 | T207
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T192 | Electrical - Task 28 | Structural Works | Prasad | 2026-01-01 | 2026-01-06 | 3 | Open | 1047 | 10 | Feet | Electrical - Task 28 execution and completion | Low | T93 | SS | 0
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Electrical | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T193 | Electrical - Task 29 | Electrical | Prasad | 2026-01-01 | 2026-01-10 | 3 | Quantity | 3076 | 10 | Kilogram | Electrical - Task 29 execution and completion | Medium | T150 | FS | -2 | T218,T260,T271
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T194 | Plumbing - Task 1 | Structural Works | Prasad | 2026-01-14 | 2026-01-19 | 3 | Open | 4925 | 10 | Meter | Plumbing - Task 1 execution and completion | Medium | T165,T143,T185 | SF,SF,FS | 5,3,3
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T195 | Plumbing - Task 2 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-10 | 3 | Quantity | 4420 | 10 | Feet | Plumbing - Task 2 execution and completion | Low | T141,T157 | SS,FS | 1,2 | T259,T279
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T196 | Plumbing - Task 3 | Preliminaries & Site Works | Prasad | 2026-01-01 | 2026-01-04 | 3 | Open | 133 | 10 | Kilogram | Plumbing - Task 3 execution and completion | High |  |  |  | T251
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T197 | Plumbing - Task 4 | Structural Works | Prasad | 2026-01-01 | 2026-01-10 | 3 | Quantity | 489 | 10 | Square Meter | Plumbing - Task 4 execution and completion | Medium | T156 | SS | 4 | T233
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T198 | Plumbing - Task 5 | Preliminaries & Site Works | Prasad | 2026-01-01 | 2026-01-11 | 3 | Open | 1080 | 10 | Numbers | Plumbing - Task 5 execution and completion | Low | T161,T138,T163 | FS,FS,FS | 0,4,-2 | T210
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T199 | Plumbing - Task 6 | Electrical | Prasad | 2026-01-01 | 2026-01-05 | 3 | Open | 1499 | 10 | Kilogram | Plumbing - Task 6 execution and completion | High | T130 | SS | -1 | T243
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T200 | Plumbing - Task 7 | Structural Works | Prasad | 2026-01-01 | 2026-01-07 | 3 | Quantity | 4441 | 10 | Square Meter | Plumbing - Task 7 execution and completion | Low |  |  |  | T224
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T201 | Plumbing - Task 8 | Structural Works | Prasad | 2026-01-01 | 2026-01-09 | 3 | Open | 3643 | 10 | Feet | Plumbing - Task 8 execution and completion | High | T119 | FS | 7 | T217
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T202 | Plumbing - Task 9 | Finishing | Prasad | 2026-01-15 | 2026-01-21 | 3 | Quantity | 220 | 10 | Kilogram | Plumbing - Task 9 execution and completion | Low | T180,T161 | FS,FS | 7,7
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T203 | Plumbing - Task 10 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-06 | 3 | Open | 3982 | 10 | Kilogram | Plumbing - Task 10 execution and completion | Low | T161 | SS | 4
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T204 | Plumbing - Task 11 | Electrical | Prasad | 2026-01-06 | 2026-01-08 | 3 | Quantity | 3736 | 10 | Meter | Plumbing - Task 11 execution and completion | Low | T190 | SS | 5 | T244,T275
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T205 | Plumbing - Task 12 | Structural Works | Prasad | 2026-01-03 | 2026-01-05 | 3 | Open | 553 | 10 | Cubic Meter | Plumbing - Task 12 execution and completion | Medium | T172 | SS | 2
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T206 | Plumbing - Task 13 | HVAC Systems | Prasad | 2026-01-06 | 2026-01-16 | 3 | Quantity | 1742 | 10 | Numbers | Plumbing - Task 13 execution and completion | Medium | T159,T171 | FS,FS | 7,3
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T207 | Plumbing - Task 14 | Architectural Works | Prasad | 2026-01-04 | 2026-01-07 | 3 | Open | 1750 | 10 | Square Meter | Plumbing - Task 14 execution and completion | Low | T191 | FS | -2 | T256,T284
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T208 | Plumbing - Task 15 | Structural Works | Prasad | 2026-01-01 | 2026-01-03 | 3 | Quantity | 2924 | 10 | Kilogram | Plumbing - Task 15 execution and completion | Medium |  |  |  | T219,T233,T274
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T209 | Plumbing - Task 16 | Structural Works | Prasad | 2026-01-01 | 2026-01-11 | 3 | Open | 2406 | 10 | Feet | Plumbing - Task 16 execution and completion | Medium
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T210 | Plumbing - Task 17 | External Development | Prasad | 2026-01-11 | 2026-01-14 | 3 | Open | 45 | 10 | Cubic Meter | Plumbing - Task 17 execution and completion | Medium | T198,T152 | FS,FS | 0,-2
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T211 | Plumbing - Task 18 | Preliminaries & Site Works | Vamsi | 2026-01-12 | 2026-01-14 | 3 | Quantity | 1730 | 10 | Cubic Meter | Plumbing - Task 18 execution and completion | Low | T184 | FS | 6 | T219,T222,T258
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T212 | Plumbing - Task 19 | Structural Works | Vamsi | 2026-01-13 | 2026-01-17 | 3 | Open | 1880 | 10 | Numbers | Plumbing - Task 19 execution and completion | High | T117,T168,T171 | FS,FS,SS | 4,6,-2 | T309
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T213 | Plumbing - Task 20 | Plumbing & Sanitary | Vamsi | 2026-01-01 | 2026-01-11 | 3 | Quantity | 2327 | 10 | Feet | Plumbing - Task 20 execution and completion | Medium | T131 | FS | 4
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T214 | Plumbing - Task 21 | Electrical | Vamsi | 2026-01-01 | 2026-01-07 | 3 | Open | 4258 | 10 | Meter | Plumbing - Task 21 execution and completion | Medium | T120,T163 | FS,SS | 2,0 | T222,T266
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T215 | Plumbing - Task 22 | Structural Works | Vamsi | 2026-01-01 | 2026-01-05 | 3 | Quantity | 1486 | 10 | Meter | Plumbing - Task 22 execution and completion | High | T144 | SF | 7 | T224
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T216 | Plumbing - Task 23 | Structural Works | Vamsi | 2026-01-01 | 2026-01-04 | 3 | Open | 572 | 10 | Feet | Plumbing - Task 23 execution and completion | High | T174 | SS | -2 | T294
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T217 | Plumbing - Task 24 | Architectural Works | Vamsi | 2026-01-01 | 2026-01-14 | 3 | Quantity | 40 | 10 | Feet | Plumbing - Task 24 execution and completion | Medium | T201 | FF | 5 | T231,T236,T299
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T218 | Plumbing - Task 25 | External Development | Vamsi | 2026-01-12 | 2026-01-21 | 3 | Open | 60 | 10 | Feet | Plumbing - Task 25 execution and completion | High | T165,T193 | FS,FS | 3,2 | T306
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T219 | Plumbing - Task 26 | Structural Works | Vamsi | 2026-01-12 | 2026-01-20 | 3 | Quantity | 2885 | 10 | Meter | Plumbing - Task 26 execution and completion | Medium | T208,T177,T211 | FF,FS,FS | 1,4,-2 | T262,T292
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T220 | Plumbing - Task 27 | Electrical | Vamsi | 2026-01-01 | 2026-01-05 | 2 | Open | 2243 | 10 | Meter | Plumbing - Task 27 execution and completion | Low |  |  |  | T254,T277
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T221 | Plumbing - Task 28 | Architectural Works | Vamsi | 2026-01-01 | 2026-01-11 | 2 | Open | 1146 | 10 | Feet | Plumbing - Task 28 execution and completion | Medium | T149 | FS | 3 | T260
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T222 | Plumbing - Task 29 | Electrical | Vamsi | 2026-01-21 | 2026-01-23 | 2 | Quantity | 4627 | 10 | Numbers | Plumbing - Task 29 execution and completion | Medium | T211,T214 | FS,FS | 7,7
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T223 | Plumbing - Task 30 | Electrical | Vamsi | 2026-01-01 | 2026-01-09 | 2 | Open | 861 | 10 | Numbers | Plumbing - Task 30 execution and completion | High | T165 | FF | 1 | T235,T290,T293
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T224 | Plumbing - Task 31 | Plumbing & Sanitary | Vamsi | 2026-01-05 | 2026-01-13 | 2 | Quantity | 3529 | 10 | Kilogram | Plumbing - Task 31 execution and completion | Low | T215,T200,T175 | FS,FS,SS | -1,-2,0
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T225 | Plumbing - Task 32 | Electrical | Vamsi | 2026-01-01 | 2026-01-04 | 2 | Open | 3297 | 10 | Feet | Plumbing - Task 32 execution and completion | High |  |  |  | T282,T283,T308
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T226 | Plumbing - Task 33 | HVAC Systems | Vamsi | 2026-01-01 | 2026-01-05 | 2 | Quantity | 825 | 10 | Feet | Plumbing - Task 33 execution and completion | Low | T147,T134 | FS,FS | 1,2 | T280,T285
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T227 | Plumbing - Task 34 | Electrical | Vamsi | 2026-01-01 | 2026-01-05 | 2 | Open | 843 | 10 | Cubic Meter | Plumbing - Task 34 execution and completion | High | T126 | FS | 5 | T269,T299
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T228 | Plumbing - Task 35 | External Development | Vamsi | 2026-01-01 | 2026-01-09 | 2 | Quantity | 881 | 10 | Numbers | Plumbing - Task 35 execution and completion | High |  |  |  | T254,T287,T291
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T229 | Plumbing - Task 36 | Structural Works | Prasad | 2026-01-11 | 2026-01-21 | 2 | Open | 4158 | 10 | Numbers | Plumbing - Task 36 execution and completion | High | T164,T140,T185 | FS,SS,FS | 5,-1,0
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | Plumbing | Bhargavi | 2026-01-01 | 2026-06-30 | 35 | T230 | Plumbing - Task 37 | External Development | Prasad | 2026-01-01 | 2026-01-10 | 2 | Quantity | 2785 | 10 | Feet | Plumbing - Task 37 execution and completion | Low | T144 | FS | -1 | T232
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Bhargavi | 2026-01-01 | 2026-06-30 | 30 | T231 | HVAC - Task 1 | External Development | Prasad | 2026-01-13 | 2026-01-20 | 4 | Open | 4689 | 10 | Meter | HVAC - Task 1 execution and completion | Medium | T217,T151,T182 | FF,FS,FS | 1,1,7 | T260,T262
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Bhargavi | 2026-01-01 | 2026-06-30 | 30 | T232 | HVAC - Task 2 | Preliminaries & Site Works | Prasad | 2026-01-16 | 2026-01-26 | 4 | Open | 4741 | 10 | Square Meter | HVAC - Task 2 execution and completion | Low | T230 | FS | 6 | T271,T309
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Bhargavi | 2026-01-01 | 2026-06-30 | 30 | T233 | HVAC - Task 3 | External Development | Prasad | 2026-01-17 | 2026-01-25 | 4 | Quantity | 184 | 10 | Numbers | HVAC - Task 3 execution and completion | High | T208,T197 | FS,FS | 7,7 | T267
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Bhargavi | 2026-01-01 | 2026-06-30 | 30 | T234 | HVAC - Task 4 | Structural Works | Prasad | 2026-01-01 | 2026-01-07 | 4 | Open | 1453 | 10 | Meter | HVAC - Task 4 execution and completion | Medium |  |  |  | T237
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Bhargavi | 2026-01-01 | 2026-06-30 | 30 | T235 | HVAC - Task 5 | HVAC Systems | Prasad | 2026-01-07 | 2026-01-13 | 4 | Quantity | 2245 | 10 | Meter | HVAC - Task 5 execution and completion | High | T223 | FS | -2
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T236 | HVAC - Task 6 | Preliminaries & Site Works | Prasad | 2026-01-20 | 2026-01-23 | 4 | Open | 2196 | 10 | Cubic Meter | HVAC - Task 6 execution and completion | Low | T217 | FS | 6 | T243
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T237 | HVAC - Task 7 | Structural Works | Prasad | 2026-01-11 | 2026-01-20 | 4 | Quantity | 2052 | 10 | Kilogram | HVAC - Task 7 execution and completion | Medium | T234 | FS | 4 | T300
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T238 | HVAC - Task 8 | Electrical | Prasad | 2026-01-13 | 2026-01-18 | 4 | Open | 2934 | 10 | Meter | HVAC - Task 8 execution and completion | High | T190 | FS | 3 | T246,T274
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T239 | HVAC - Task 9 | External Development | Prasad | 2026-01-01 | 2026-01-04 | 4 | Quantity | 2813 | 10 | Feet | HVAC - Task 9 execution and completion | High |  |  |  | T256
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T240 | HVAC - Task 10 | Electrical | Prasad | 2026-01-01 | 2026-01-03 | 4 | Open | 3955 | 10 | Cubic Meter | HVAC - Task 10 execution and completion | High
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T241 | HVAC - Task 11 | Structural Works | Prasad | 2026-01-01 | 2026-01-05 | 4 | Quantity | 99 | 10 | Kilogram | HVAC - Task 11 execution and completion | High
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T242 | HVAC - Task 12 | Structural Works | Prasad | 2026-01-01 | 2026-01-09 | 4 | Open | 2161 | 10 | Meter | HVAC - Task 12 execution and completion | Low | T170,T151,T164 | SF,FS,FS | 6,7,-2 | T292
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T243 | HVAC - Task 13 | Architectural Works | Prasad | 2026-01-27 | 2026-02-04 | 4 | Open | 2397 | 10 | Numbers | HVAC - Task 13 execution and completion | Medium | T199,T236 | SS,FS | 2,4 | T250,T275
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T244 | HVAC - Task 14 | HVAC Systems | Prasad | 2026-01-01 | 2026-01-04 | 4 | Quantity | 2618 | 10 | Feet | HVAC - Task 14 execution and completion | Low | T204 | SF | -2 | T331
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T245 | HVAC - Task 15 | External Development | Prasad | 2026-01-01 | 2026-01-03 | 4 | Open | 3819 | 10 | Numbers | HVAC - Task 15 execution and completion | High | T161 | FS | -2 | T292
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T246 | HVAC - Task 16 | Finishing | Prasad | 2026-01-23 | 2026-02-02 | 4 | Quantity | 4409 | 10 | Numbers | HVAC - Task 16 execution and completion | High | T238 | FS | 5 | T273,T279,T353
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T247 | HVAC - Task 17 | Electrical | Prasad | 2026-01-11 | 2026-01-21 | 4 | Open | 3474 | 10 | Feet | HVAC - Task 17 execution and completion | Low | T169 | FS | 0
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T248 | HVAC - Task 18 | External Development | Prasad | 2026-01-01 | 2026-01-11 | 4 | Quantity | 2831 | 10 | Square Meter | HVAC - Task 18 execution and completion | Low | T163 | SF | 0 | T284
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T249 | HVAC - Task 19 | Preliminaries & Site Works | Prasad | 2026-01-01 | 2026-01-10 | 4 | Open | 2953 | 10 | Square Meter | HVAC - Task 19 execution and completion | High |  |  |  | T263,T343
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T250 | HVAC - Task 20 | Electrical | Prasad | 2026-02-10 | 2026-02-13 | 4 | Quantity | 1550 | 10 | Numbers | HVAC - Task 20 execution and completion | Low | T243 | FS | 6 | T261,T308
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T251 | HVAC - Task 21 | Structural Works | Prasad | 2026-01-07 | 2026-01-16 | 4 | Open | 3157 | 10 | Meter | HVAC - Task 21 execution and completion | Low | T196 | FS | 3 | T269,T275
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T252 | HVAC - Task 22 | Architectural Works | Prasad | 2026-01-07 | 2026-01-10 | 4 | Quantity | 3577 | 10 | Square Meter | HVAC - Task 22 execution and completion | Medium | T171 | FS | 4
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T253 | HVAC - Task 23 | Finishing | Vamsi | 2026-01-01 | 2026-01-08 | 4 | Open | 4863 | 10 | Square Meter | HVAC - Task 23 execution and completion | High |  |  |  | T265,T293
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T254 | HVAC - Task 24 | Plumbing & Sanitary | Vamsi | 2026-01-12 | 2026-01-18 | 4 | Open | 2264 | 10 | Kilogram | HVAC - Task 24 execution and completion | Medium | T228,T220 | FF,FS | 6,7
MEP Works | Bharath | 2026-01-01 | 2026-06-30 | 20 | HVAC | Mahesh | 2026-01-01 | 2026-06-30 | 30 | T255 | HVAC - Task 25 | HVAC Systems | Vamsi | 2026-01-13 | 2026-01-19 | 4 | Quantity | 4516 | 10 | Kilogram | HVAC - Task 25 execution and completion | Medium | T180 | FS | 5 | T303
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T256 | Flooring - Task 1 | Electrical | Vamsi | 2026-07-01 | 2026-07-03 | 3 | Open | 1406 | 10 | Feet | Flooring - Task 1 execution and completion | Medium | T239,T207 | FF,FS | 6,6 | T307,T352
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T257 | Flooring - Task 2 | Architectural Works | Vamsi | 2026-07-01 | 2026-07-09 | 3 | Quantity | 1470 | 10 | Cubic Meter | Flooring - Task 2 execution and completion | Medium |  |  |  | T328,T338
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T258 | Flooring - Task 3 | Structural Works | Vamsi | 2026-07-01 | 2026-07-06 | 3 | Open | 834 | 10 | Feet | Flooring - Task 3 execution and completion | High | T211 | SF | 1 | T315
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T259 | Flooring - Task 4 | Architectural Works | Vamsi | 2026-07-01 | 2026-07-10 | 3 | Quantity | 2378 | 10 | Feet | Flooring - Task 4 execution and completion | Low | T195 | FS | 5 | T267
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T260 | Flooring - Task 5 | Plumbing & Sanitary | Vamsi | 2026-07-01 | 2026-07-07 | 3 | Open | 1300 | 10 | Square Meter | Flooring - Task 5 execution and completion | Low | T193,T221,T231 | FS,SS,FS | 5,4,6 | T282,T304,T327
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T261 | Flooring - Task 6 | Structural Works | Vamsi | 2026-07-01 | 2026-07-04 | 3 | Quantity | 4229 | 10 | Cubic Meter | Flooring - Task 6 execution and completion | High | T250 | FS | 2
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T262 | Flooring - Task 7 | Electrical | Vamsi | 2026-07-01 | 2026-07-06 | 3 | Open | 2356 | 10 | Meter | Flooring - Task 7 execution and completion | Low | T219,T231,T179 | SS,FF,FS | 1,2,6
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T263 | Flooring - Task 8 | HVAC Systems | Vamsi | 2026-07-01 | 2026-07-07 | 3 | Quantity | 1733 | 10 | Feet | Flooring - Task 8 execution and completion | Low | T249 | FS | 4 | T293,T348
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T264 | Flooring - Task 9 | Preliminaries & Site Works | Vamsi | 2026-07-01 | 2026-07-03 | 3 | Open | 4841 | 10 | Feet | Flooring - Task 9 execution and completion | Low |  |  |  | T270
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T265 | Flooring - Task 10 | Structural Works | Vamsi | 2026-07-01 | 2026-07-06 | 3 | Open | 2413 | 10 | Numbers | Flooring - Task 10 execution and completion | Low | T182,T253 | FS,SS | 5,4 | T317
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T266 | Flooring - Task 11 | Electrical | Vamsi | 2026-07-01 | 2026-07-07 | 3 | Quantity | 2741 | 10 | Square Meter | Flooring - Task 11 execution and completion | Medium | T214 | FS | 5 | T290
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T267 | Flooring - Task 12 | Structural Works | Vamsi | 2026-07-08 | 2026-07-12 | 3 | Open | 4067 | 10 | Numbers | Flooring - Task 12 execution and completion | Medium | T233,T259,T185 | FS,FS,FS | 7,-2,5 | T310,T346
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T268 | Flooring - Task 13 | Plumbing & Sanitary | Vamsi | 2026-07-01 | 2026-07-09 | 3 | Quantity | 773 | 10 | Square Meter | Flooring - Task 13 execution and completion | Medium |  |  |  | T337
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T269 | Flooring - Task 14 | Structural Works | Vamsi | 2026-07-01 | 2026-07-05 | 3 | Open | 641 | 10 | Numbers | Flooring - Task 14 execution and completion | Medium | T227,T251 | FS,FS | 7,-2
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T270 | Flooring - Task 15 | Preliminaries & Site Works | Vamsi | 2026-07-07 | 2026-07-13 | 3 | Quantity | 4116 | 10 | Numbers | Flooring - Task 15 execution and completion | Medium | T264 | FS | 4 | T328
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T271 | Flooring - Task 16 | Structural Works | Prasad | 2026-07-01 | 2026-07-06 | 3 | Open | 2383 | 10 | Square Meter | Flooring - Task 16 execution and completion | Medium | T193,T232 | FS,SF | 1,7
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T272 | Flooring - Task 17 | HVAC Systems | Prasad | 2026-07-01 | 2026-07-08 | 3 | Quantity | 1586 | 10 | Cubic Meter | Flooring - Task 17 execution and completion | Medium |  |  |  | T345
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T273 | Flooring - Task 18 | Structural Works | Prasad | 2026-07-01 | 2026-07-09 | 3 | Open | 4826 | 10 | Kilogram | Flooring - Task 18 execution and completion | High | T246 | FS | 6 | T289,T291,T332,T358
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T274 | Flooring - Task 19 | Architectural Works | Prasad | 2026-07-01 | 2026-07-05 | 3 | Quantity | 4573 | 10 | Feet | Flooring - Task 19 execution and completion | Medium | T208,T238 | SS,FS | 5,7 | T299,T312,T341
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T275 | Flooring - Task 20 | Structural Works | Prasad | 2026-07-01 | 2026-07-08 | 3 | Open | 616 | 10 | Feet | Flooring - Task 20 execution and completion | Low | T251,T243,T204 | FS,SS,SS | 4,7,-1 | T318
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T276 | Flooring - Task 21 | Plumbing & Sanitary | Prasad | 2026-07-01 | 2026-07-09 | 3 | Open | 3185 | 10 | Feet | Flooring - Task 21 execution and completion | Medium |  |  |  | T282
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T277 | Flooring - Task 22 | Architectural Works | Prasad | 2026-07-01 | 2026-07-05 | 3 | Quantity | 785 | 10 | Meter | Flooring - Task 22 execution and completion | Low | T220,T188 | FS,FS | 0,3
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T278 | Flooring - Task 23 | Structural Works | Prasad | 2026-07-01 | 2026-07-03 | 3 | Open | 3413 | 10 | Feet | Flooring - Task 23 execution and completion | Medium |  |  |  | T279,T298,T306
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T279 | Flooring - Task 24 | Preliminaries & Site Works | Prasad | 2026-07-04 | 2026-07-09 | 3 | Quantity | 3810 | 10 | Numbers | Flooring - Task 24 execution and completion | Medium | T195,T278,T246 | SS,SS,FS | 1,3,-1 | T310,T337,T352
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T280 | Flooring - Task 25 | Structural Works | Prasad | 2026-07-01 | 2026-07-03 | 3 | Open | 2173 | 10 | Kilogram | Flooring - Task 25 execution and completion | Medium | T226 | SF | 1
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T281 | Flooring - Task 26 | Structural Works | Prasad | 2026-07-01 | 2026-07-09 | 3 | Quantity | 4374 | 10 | Square Meter | Flooring - Task 26 execution and completion | High | T182 | FS | 4
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T282 | Flooring - Task 27 | Electrical | Prasad | 2026-07-12 | 2026-07-16 | 3 | Open | 698 | 10 | Kilogram | Flooring - Task 27 execution and completion | High | T260,T225,T276 | FS,FS,FS | 0,-1,3
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T283 | Flooring - Task 28 | External Development | Prasad | 2026-07-01 | 2026-07-09 | 3 | Quantity | 88 | 10 | Cubic Meter | Flooring - Task 28 execution and completion | Medium | T180,T225 | FS,FS | -2,0 | T305,T330
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T284 | Flooring - Task 29 | Structural Works | Prasad | 2026-07-01 | 2026-07-03 | 3 | Open | 3952 | 10 | Meter | Flooring - Task 29 execution and completion | Medium | T184,T248,T207 | FS,FS,FS | 5,4,0 | T289,T373
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T285 | Flooring - Task 30 | Plumbing & Sanitary | Prasad | 2026-07-01 | 2026-07-07 | 3 | Quantity | 2716 | 10 | Numbers | Flooring - Task 30 execution and completion | Low | T226 | SS | 4 | T295,T380
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T286 | Flooring - Task 31 | Electrical | Prasad | 2026-07-01 | 2026-07-07 | 3 | Open | 967 | 10 | Kilogram | Flooring - Task 31 execution and completion | High | T187 | FS | -2 | T357
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T287 | Flooring - Task 32 | Electrical | Prasad | 2026-07-01 | 2026-07-04 | 3 | Open | 3069 | 10 | Kilogram | Flooring - Task 32 execution and completion | High | T228,T183 | FS,FS | 2,7 | T356
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Thej | 2026-07-01 | 2026-12-31 | 35 | T288 | Flooring - Task 33 | Plumbing & Sanitary | Prasad | 2026-07-01 | 2026-07-06 | 2 | Quantity | 1755 | 10 | Feet | Flooring - Task 33 execution and completion | Medium |  |  |  | T301,T355,T365
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Flooring | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T289 | Flooring - Task 34 | Structural Works | Prasad | 2026-07-01 | 2026-07-13 | 2 | Open | 3042 | 10 | Meter | Flooring - Task 34 execution and completion | High | T284,T273 | FF,FF | 2,4 | T320,T375
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T290 | Painting - Task 1 | Finishing | Prasad | 2026-07-10 | 2026-07-20 | 4 | Quantity | 4071 | 10 | Feet | Painting - Task 1 execution and completion | High | T223,T266 | FS,FS | 4,3 | T295,T378
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T291 | Painting - Task 2 | Structural Works | Prasad | 2026-07-09 | 2026-07-11 | 4 | Open | 3434 | 10 | Square Meter | Painting - Task 2 execution and completion | Low | T273,T228 | FS,FS | 0,3
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T292 | Painting - Task 3 | Electrical | Prasad | 2026-07-01 | 2026-07-06 | 4 | Quantity | 1527 | 10 | Meter | Painting - Task 3 execution and completion | Medium | T219,T245,T242 | FS,SS,FS | 1,-1,6 | T330
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T293 | Painting - Task 4 | HVAC Systems | Prasad | 2026-07-05 | 2026-07-12 | 4 | Open | 3412 | 10 | Cubic Meter | Painting - Task 4 execution and completion | High | T263,T223,T253 | FS,FS,FS | -2,1,1
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T294 | Painting - Task 5 | Finishing | Prasad | 2026-07-01 | 2026-07-03 | 4 | Quantity | 513 | 10 | Meter | Painting - Task 5 execution and completion | Low | T216 | SS | 6
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T295 | Painting - Task 6 | External Development | Prasad | 2026-07-21 | 2026-07-27 | 4 | Open | 1322 | 10 | Numbers | Painting - Task 6 execution and completion | High | T290,T285 | FS,FS | 1,-2
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T296 | Painting - Task 7 | External Development | Prasad | 2026-07-01 | 2026-07-10 | 4 | Quantity | 1070 | 10 | Square Meter | Painting - Task 7 execution and completion | Low
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T297 | Painting - Task 8 | Preliminaries & Site Works | Prasad | 2026-07-01 | 2026-07-11 | 3 | Open | 3690 | 10 | Kilogram | Painting - Task 8 execution and completion | High |  |  |  | T360
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T298 | Painting - Task 9 | External Development | Prasad | 2026-07-04 | 2026-07-10 | 3 | Open | 4974 | 10 | Cubic Meter | Painting - Task 9 execution and completion | Medium | T278 | SS | 3 | T306
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T299 | Painting - Task 10 | Electrical | Prasad | 2026-07-09 | 2026-07-17 | 3 | Quantity | 2725 | 10 | Cubic Meter | Painting - Task 10 execution and completion | Medium | T217,T227,T274 | SS,FS,FS | -1,3,4
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T300 | Painting - Task 11 | HVAC Systems | Prasad | 2026-07-01 | 2026-07-07 | 3 | Open | 52 | 10 | Square Meter | Painting - Task 11 execution and completion | Low | T237 | FS | 5 | T359
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T301 | Painting - Task 12 | External Development | Prasad | 2026-07-10 | 2026-07-19 | 3 | Quantity | 3919 | 10 | Cubic Meter | Painting - Task 12 execution and completion | Low | T288 | FS | 4 | T379
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T302 | Painting - Task 13 | External Development | Prasad | 2026-07-01 | 2026-07-09 | 3 | Open | 4074 | 10 | Kilogram | Painting - Task 13 execution and completion | Medium |  |  |  | T381
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T303 | Painting - Task 14 | Finishing | Vamsi | 2026-07-01 | 2026-07-07 | 3 | Quantity | 437 | 10 | Kilogram | Painting - Task 14 execution and completion | High | T255 | FS | 3 | T307,T354,T357
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T304 | Painting - Task 15 | Architectural Works | Vamsi | 2026-07-11 | 2026-07-13 | 3 | Open | 1341 | 10 | Kilogram | Painting - Task 15 execution and completion | Medium | T260 | FS | 4
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T305 | Painting - Task 16 | Structural Works | Vamsi | 2026-07-15 | 2026-07-23 | 3 | Quantity | 1848 | 10 | Cubic Meter | Painting - Task 16 execution and completion | Medium | T283 | FS | 6 | T313,T389
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T306 | Painting - Task 17 | Structural Works | Vamsi | 2026-07-09 | 2026-07-13 | 3 | Open | 4459 | 10 | Square Meter | Painting - Task 17 execution and completion | High | T298,T278,T218 | FS,FS,FS | -1,0,7
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T307 | Painting - Task 18 | Structural Works | Vamsi | 2026-07-10 | 2026-07-18 | 3 | Quantity | 387 | 10 | Square Meter | Painting - Task 18 execution and completion | Low | T303,T256 | FS,FS | 3,-1 | T330,T400
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T308 | Painting - Task 19 | Structural Works | Vamsi | 2026-07-01 | 2026-07-10 | 3 | Open | 4265 | 10 | Feet | Painting - Task 19 execution and completion | Medium | T225,T250 | SS,FS | 6,0 | T313
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T309 | Painting - Task 20 | HVAC Systems | Vamsi | 2026-07-01 | 2026-07-04 | 3 | Open | 1836 | 10 | Square Meter | Painting - Task 20 execution and completion | High | T212,T232 | SS,SS | 6,-2 | T321,T382
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T310 | Painting - Task 21 | Architectural Works | Vamsi | 2026-07-19 | 2026-07-21 | 3 | Quantity | 3618 | 10 | Square Meter | Painting - Task 21 execution and completion | Low | T267,T279 | FS,FS | 7,6
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T311 | Painting - Task 22 | Finishing | Vamsi | 2026-07-01 | 2026-07-06 | 3 | Open | 3222 | 10 | Feet | Painting - Task 22 execution and completion | High |  |  |  | T323
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T312 | Painting - Task 23 | Structural Works | Vamsi | 2026-07-01 | 2026-07-07 | 3 | Quantity | 1165 | 10 | Feet | Painting - Task 23 execution and completion | Medium | T274 | FF | 1 | T353
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T313 | Painting - Task 24 | Preliminaries & Site Works | Vamsi | 2026-07-28 | 2026-07-31 | 3 | Open | 1113 | 10 | Kilogram | Painting - Task 24 execution and completion | High | T305,T308 | FS,SS | 5,-1 | T350,T392
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T314 | Painting - Task 25 | Preliminaries & Site Works | Vamsi | 2026-07-01 | 2026-07-09 | 3 | Quantity | 1963 | 10 | Numbers | Painting - Task 25 execution and completion | High |  |  |  | T381
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T315 | Painting - Task 26 | Structural Works | Vamsi | 2026-07-01 | 2026-07-04 | 3 | Open | 1215 | 10 | Meter | Painting - Task 26 execution and completion | High | T258 | SF | -1
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T316 | Painting - Task 27 | Plumbing & Sanitary | Vamsi | 2026-07-01 | 2026-07-05 | 3 | Quantity | 3318 | 10 | Meter | Painting - Task 27 execution and completion | Low |  |  |  | T329,T365
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T317 | Painting - Task 28 | Finishing | Vamsi | 2026-07-07 | 2026-07-10 | 3 | Open | 2106 | 10 | Square Meter | Painting - Task 28 execution and completion | Low | T265 | FS | 1 | T391
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T318 | Painting - Task 29 | Architectural Works | Vamsi | 2026-07-14 | 2026-07-23 | 3 | Quantity | 4426 | 10 | Square Meter | Painting - Task 29 execution and completion | Medium | T275 | FS | 6 | T325,T384,T397
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T319 | Painting - Task 30 | Architectural Works | Vamsi | 2026-07-01 | 2026-07-09 | 3 | Open | 3946 | 10 | Feet | Painting - Task 30 execution and completion | High |  |  |  | T344,T360
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Painting | Mahesh | 2026-07-01 | 2026-12-31 | 35 | T320 | Painting - Task 31 | Architectural Works | Vamsi | 2026-07-16 | 2026-07-23 | 3 | Open | 1244 | 10 | Numbers | Painting - Task 31 execution and completion | Low | T289 | FS | 3 | T349,T370
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T321 | Carpentry - Task 1 | Preliminaries & Site Works | Prasad | 2026-07-06 | 2026-07-11 | 3 | Quantity | 1651 | 10 | Square Meter | Carpentry - Task 1 execution and completion | High | T309 | FS | 2 | T343
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T322 | Carpentry - Task 2 | Electrical | Prasad | 2026-07-01 | 2026-07-08 | 3 | Open | 1769 | 10 | Cubic Meter | Carpentry - Task 2 execution and completion | Low |  |  |  | T333,T365,T405
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T323 | Carpentry - Task 3 | Plumbing & Sanitary | Prasad | 2026-07-06 | 2026-07-14 | 3 | Quantity | 870 | 10 | Numbers | Carpentry - Task 3 execution and completion | High | T311 | SS | 5 | T327
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T324 | Carpentry - Task 4 | Preliminaries & Site Works | Prasad | 2026-07-01 | 2026-07-04 | 3 | Open | 1779 | 10 | Square Meter | Carpentry - Task 4 execution and completion | Low |  |  |  | T353
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T325 | Carpentry - Task 5 | HVAC Systems | Prasad | 2026-07-30 | 2026-08-06 | 3 | Quantity | 514 | 10 | Cubic Meter | Carpentry - Task 5 execution and completion | Low | T318 | FS | 7
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T326 | Carpentry - Task 6 | Structural Works | Prasad | 2026-07-01 | 2026-07-05 | 3 | Open | 4180 | 10 | Square Meter | Carpentry - Task 6 execution and completion | Low |  |  |  | T351,T394
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T327 | Carpentry - Task 7 | Structural Works | Prasad | 2026-07-21 | 2026-07-31 | 3 | Quantity | 757 | 10 | Meter | Carpentry - Task 7 execution and completion | Low | T323,T260 | FS,FS | 7,0 | T403
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T328 | Carpentry - Task 8 | Structural Works | Prasad | 2026-07-16 | 2026-07-25 | 3 | Open | 4801 | 10 | Kilogram | Carpentry - Task 8 execution and completion | Medium | T257,T270 | FS,FS | 2,3 | T387
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T329 | Carpentry - Task 9 | HVAC Systems | Prasad | 2026-07-06 | 2026-07-14 | 3 | Quantity | 3911 | 10 | Numbers | Carpentry - Task 9 execution and completion | Low | T316 | FS | 1 | T400
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T330 | Carpentry - Task 10 | Preliminaries & Site Works | Prasad | 2026-07-18 | 2026-07-20 | 3 | Open | 4829 | 10 | Numbers | Carpentry - Task 10 execution and completion | Low | T292,T283,T307 | FS,FS,FS | 1,6,0 | T333
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T331 | Carpentry - Task 11 | Finishing | Prasad | 2026-07-01 | 2026-07-11 | 3 | Open | 1217 | 10 | Meter | Carpentry - Task 11 execution and completion | Medium | T244 | FS | 3
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T332 | Carpentry - Task 12 | External Development | Prasad | 2026-07-13 | 2026-07-20 | 3 | Quantity | 3918 | 10 | Feet | Carpentry - Task 12 execution and completion | High | T273 | FS | 4 | T372
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T333 | Carpentry - Task 13 | Structural Works | Prasad | 2026-07-27 | 2026-08-06 | 3 | Open | 4381 | 10 | Numbers | Carpentry - Task 13 execution and completion | Low | T330,T322 | FS,FS | 7,-1 | T402
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T334 | Carpentry - Task 14 | External Development | Prasad | 2026-07-01 | 2026-07-07 | 3 | Quantity | 2766 | 10 | Feet | Carpentry - Task 14 execution and completion | Medium |  |  |  | T414
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T335 | Carpentry - Task 15 | Architectural Works | Prasad | 2026-07-01 | 2026-07-06 | 3 | Open | 3695 | 10 | Numbers | Carpentry - Task 15 execution and completion | High
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T336 | Carpentry - Task 16 | Structural Works | Prasad | 2026-07-01 | 2026-07-10 | 3 | Quantity | 4316 | 10 | Numbers | Carpentry - Task 16 execution and completion | High |  |  |  | T377,T438
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T337 | Carpentry - Task 17 | Electrical | Prasad | 2026-07-09 | 2026-07-17 | 3 | Open | 3521 | 10 | Square Meter | Carpentry - Task 17 execution and completion | High | T279,T268 | FS,FS | 0,-1
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T338 | Carpentry - Task 18 | HVAC Systems | Prasad | 2026-07-15 | 2026-07-17 | 3 | Quantity | 1954 | 10 | Meter | Carpentry - Task 18 execution and completion | Medium | T257 | FS | 6 | T382
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T339 | Carpentry - Task 19 | Preliminaries & Site Works | Prasad | 2026-07-01 | 2026-07-04 | 3 | Open | 4521 | 10 | Meter | Carpentry - Task 19 execution and completion | Medium |  |  |  | T377,T382
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T340 | Carpentry - Task 20 | HVAC Systems | Prasad | 2026-07-01 | 2026-07-10 | 3 | Quantity | 2760 | 10 | Kilogram | Carpentry - Task 20 execution and completion | Medium
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T341 | Carpentry - Task 21 | Structural Works | Prasad | 2026-07-10 | 2026-07-17 | 3 | Open | 3231 | 10 | Square Meter | Carpentry - Task 21 execution and completion | High | T274 | FS | 5 | T419
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T342 | Carpentry - Task 22 | Architectural Works | Prasad | 2026-07-01 | 2026-07-09 | 3 | Open | 2780 | 10 | Cubic Meter | Carpentry - Task 22 execution and completion | High
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T343 | Carpentry - Task 23 | Electrical | Prasad | 2026-07-10 | 2026-07-18 | 3 | Quantity | 3397 | 10 | Feet | Carpentry - Task 23 execution and completion | High | T249,T321 | FS,FS | 6,-1 | T385,T432
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T344 | Carpentry - Task 24 | Structural Works | Prasad | 2026-07-01 | 2026-07-16 | 3 | Open | 2738 | 10 | Kilogram | Carpentry - Task 24 execution and completion | Low | T319 | FF | 7 | T357
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T345 | Carpentry - Task 25 | Architectural Works | Prasad | 2026-07-03 | 2026-07-07 | 2 | Quantity | 3845 | 10 | Square Meter | Carpentry - Task 25 execution and completion | Low | T272 | SS | 2
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T346 | Carpentry - Task 26 | HVAC Systems | Prasad | 2026-07-16 | 2026-07-22 | 2 | Open | 4757 | 10 | Kilogram | Carpentry - Task 26 execution and completion | High | T267 | FS | 4 | T417,T428
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T347 | Carpentry - Task 27 | External Development | Prasad | 2026-07-01 | 2026-07-08 | 2 | Quantity | 100 | 10 | Meter | Carpentry - Task 27 execution and completion | Low |  |  |  | T373,T383,T423
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T348 | Carpentry - Task 28 | Structural Works | Prasad | 2026-07-10 | 2026-07-19 | 2 | Open | 2511 | 10 | Meter | Carpentry - Task 28 execution and completion | Low | T263 | FS | 3
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T349 | Carpentry - Task 29 | Electrical | Prasad | 2026-07-29 | 2026-08-03 | 2 | Quantity | 3076 | 10 | Kilogram | Carpentry - Task 29 execution and completion | Medium | T320 | FS | 6 | T386,T423,T432
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T350 | Carpentry - Task 30 | Structural Works | Prasad | 2026-07-01 | 2026-07-28 | 2 | Open | 3189 | 10 | Kilogram | Carpentry - Task 30 execution and completion | High | T313 | SF | 0 | T378,T415
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T351 | Carpentry - Task 31 | Plumbing & Sanitary | Prasad | 2026-07-04 | 2026-07-08 | 2 | Quantity | 2009 | 10 | Cubic Meter | Carpentry - Task 31 execution and completion | Low | T326 | SS | 3 | T384
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T352 | Carpentry - Task 32 | Preliminaries & Site Works | Prasad | 2026-07-09 | 2026-07-12 | 2 | Open | 1099 | 10 | Kilogram | Carpentry - Task 32 execution and completion | Low | T279,T256 | FS,FS | 0,4 | T366,T374
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T353 | Carpentry - Task 33 | Architectural Works | Prasad | 2026-07-10 | 2026-07-17 | 2 | Open | 1698 | 10 | Kilogram | Carpentry - Task 33 execution and completion | Low | T324,T246,T312 | FS,FS,FS | 4,6,3 | T354,T398
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T354 | Carpentry - Task 34 | Preliminaries & Site Works | Prasad | 2026-07-15 | 2026-07-24 | 2 | Quantity | 2318 | 10 | Cubic Meter | Carpentry - Task 34 execution and completion | Medium | T353,T303 | FS,FS | -2,2 | T429
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T355 | Carpentry - Task 35 | Structural Works | Prasad | 2026-07-09 | 2026-07-17 | 2 | Open | 1355 | 10 | Kilogram | Carpentry - Task 35 execution and completion | Low | T288 | FS | 3 | T364,T388,T408
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T356 | Carpentry - Task 36 | Electrical | Prasad | 2026-07-05 | 2026-07-08 | 2 | Quantity | 483 | 10 | Numbers | Carpentry - Task 36 execution and completion | Medium | T287 | FS | 1
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T357 | Carpentry - Task 37 | Structural Works | Prasad | 2026-07-22 | 2026-07-30 | 2 | Open | 3120 | 10 | Square Meter | Carpentry - Task 37 execution and completion | High | T286,T344,T303 | FS,FS,SF | 5,6,-1 | T399,T430
Finishing | Bharath | 2026-07-01 | 2026-12-31 | 20 | Carpentry | Mahesh | 2026-07-01 | 2026-12-31 | 30 | T358 | Carpentry - Task 38 | Structural Works | Prasad | 2026-07-11 | 2026-07-13 | 2 | Quantity | 3907 | 10 | Square Meter | Carpentry - Task 38 execution and completion | Low | T273 | FS | 2 | T416,T440
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T359 | Landscaping - Task 1 | External Development | Prasad | 2027-01-01 | 2027-01-06 | 5 | Open | 4215 | 10 | Kilogram | Landscaping - Task 1 execution and completion | Low | T300 | SF | 1 | T362,T371,T401,T444
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T360 | Landscaping - Task 2 | Structural Works | Prasad | 2027-01-01 | 2027-01-09 | 5 | Quantity | 4665 | 10 | Feet | Landscaping - Task 2 execution and completion | Low | T319,T297 | SS,SF | 3,4 | T376,T436
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T361 | Landscaping - Task 3 | HVAC Systems | Prasad | 2027-01-01 | 2027-01-04 | 5 | Open | 3274 | 10 | Cubic Meter | Landscaping - Task 3 execution and completion | Low
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T362 | Landscaping - Task 4 | Electrical | Prasad | 2027-01-09 | 2027-01-18 | 5 | Quantity | 3847 | 10 | Meter | Landscaping - Task 4 execution and completion | Low | T359 | FS | 3 | T366
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T363 | Landscaping - Task 5 | Architectural Works | Prasad | 2027-01-01 | 2027-01-04 | 5 | Open | 41 | 10 | Cubic Meter | Landscaping - Task 5 execution and completion | Medium
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T364 | Landscaping - Task 6 | HVAC Systems | Prasad | 2027-01-01 | 2027-01-04 | 5 | Open | 2973 | 10 | Feet | Landscaping - Task 6 execution and completion | High | T355 | FS | 1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T365 | Landscaping - Task 7 | Structural Works | Prasad | 2027-01-01 | 2027-01-08 | 5 | Quantity | 1647 | 10 | Meter | Landscaping - Task 7 execution and completion | Medium | T322,T316,T288 | FS,FS,SS | 4,5,-2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T366 | Landscaping - Task 8 | Structural Works | Prasad | 2027-01-01 | 2027-01-16 | 5 | Open | 35 | 10 | Numbers | Landscaping - Task 8 execution and completion | High | T362,T352 | SF,FF | 7,0
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T367 | Landscaping - Task 9 | Architectural Works | Prasad | 2027-01-01 | 2027-01-06 | 5 | Quantity | 3172 | 10 | Square Meter | Landscaping - Task 9 execution and completion | High |  |  |  | T376
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T368 | Landscaping - Task 10 | Preliminaries & Site Works | Prasad | 2027-01-01 | 2027-01-06 | 5 | Open | 2375 | 10 | Cubic Meter | Landscaping - Task 10 execution and completion | Medium
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T369 | Landscaping - Task 11 | Structural Works | Prasad | 2027-01-01 | 2027-01-05 | 5 | Quantity | 4089 | 10 | Feet | Landscaping - Task 11 execution and completion | Medium
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T370 | Landscaping - Task 12 | Structural Works | Prasad | 2027-01-01 | 2027-01-10 | 5 | Open | 3899 | 10 | Numbers | Landscaping - Task 12 execution and completion | Medium | T320 | SF | 7 | T439
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T371 | Landscaping - Task 13 | Structural Works | Prasad | 2027-01-12 | 2027-01-17 | 4 | Quantity | 2381 | 10 | Meter | Landscaping - Task 13 execution and completion | High | T359 | FS | 6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T372 | Landscaping - Task 14 | Architectural Works | Prasad | 2027-01-01 | 2027-01-05 | 4 | Open | 2344 | 10 | Cubic Meter | Landscaping - Task 14 execution and completion | Low | T332 | FS | 5 | T411,T418
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T373 | Landscaping - Task 15 | Plumbing & Sanitary | Prasad | 2027-01-01 | 2027-01-10 | 4 | Quantity | 4331 | 10 | Kilogram | Landscaping - Task 15 execution and completion | Low | T284,T347 | FS,FS | 7,6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T374 | Landscaping - Task 16 | Finishing | Prasad | 2027-01-01 | 2027-01-09 | 4 | Open | 177 | 10 | Kilogram | Landscaping - Task 16 execution and completion | Low | T352 | SS | 7
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T375 | Landscaping - Task 17 | Preliminaries & Site Works | Prasad | 2027-01-01 | 2027-01-10 | 4 | Open | 4094 | 10 | Numbers | Landscaping - Task 17 execution and completion | Low | T289 | FS | 5
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T376 | Landscaping - Task 18 | Structural Works | Prasad | 2027-01-01 | 2027-01-10 | 4 | Quantity | 1498 | 10 | Meter | Landscaping - Task 18 execution and completion | Low | T367,T360 | FF,SF | 0,7 | T413
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T377 | Landscaping - Task 19 | HVAC Systems | Prasad | 2027-01-01 | 2027-01-08 | 4 | Open | 3160 | 10 | Numbers | Landscaping - Task 19 execution and completion | Low | T336,T339 | FS,FF | 1,-1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T378 | Landscaping - Task 20 | Structural Works | Prasad | 2027-01-01 | 2027-01-08 | 4 | Quantity | 1081 | 10 | Kilogram | Landscaping - Task 20 execution and completion | High | T350,T290 | FS,FS | 7,4
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T379 | Landscaping - Task 21 | Preliminaries & Site Works | Prasad | 2027-01-01 | 2027-01-11 | 4 | Open | 1189 | 10 | Meter | Landscaping - Task 21 execution and completion | Medium | T301 | FS | -2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Landscaping | Mahesh | 2027-01-01 | 2027-04-30 | 40 | T380 | Landscaping - Task 22 | Structural Works | Prasad | 2027-01-01 | 2027-01-08 | 4 | Quantity | 4062 | 10 | Feet | Landscaping - Task 22 execution and completion | High | T285 | FS | 5
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T381 | Paving & Roads - Task 1 | Structural Works | Prasad | 2027-01-01 | 2027-01-03 | 4 | Open | 1110 | 10 | Square Meter | Paving & Roads - Task 1 execution and completion | Medium | T302,T314 | FS,FS | 6,1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T382 | Paving & Roads - Task 2 | External Development | Prasad | 2027-01-01 | 2027-01-08 | 4 | Quantity | 435 | 10 | Square Meter | Paving & Roads - Task 2 execution and completion | Medium | T339,T309,T338 | FS,FS,FS | 4,1,5 | T395
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T383 | Paving & Roads - Task 3 | Structural Works | Prasad | 2027-01-01 | 2027-01-08 | 4 | Open | 4219 | 10 | Numbers | Paving & Roads - Task 3 execution and completion | Low | T347 | FS | 6 | T415
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T384 | Paving & Roads - Task 4 | Preliminaries & Site Works | Prasad | 2027-01-01 | 2027-01-10 | 4 | Quantity | 3974 | 10 | Square Meter | Paving & Roads - Task 4 execution and completion | Low | T351,T318 | FS,SF | 3,2 | T415
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T385 | Paving & Roads - Task 5 | Structural Works | Prasad | 2027-01-01 | 2027-01-05 | 4 | Open | 69 | 10 | Meter | Paving & Roads - Task 5 execution and completion | High | T343 | FS | 3
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T386 | Paving & Roads - Task 6 | Electrical | Prasad | 2027-01-01 | 2027-01-04 | 4 | Open | 556 | 10 | Kilogram | Paving & Roads - Task 6 execution and completion | Low | T349 | FS | 7
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T387 | Paving & Roads - Task 7 | Structural Works | Prasad | 2027-01-01 | 2027-01-11 | 4 | Quantity | 2336 | 10 | Square Meter | Paving & Roads - Task 7 execution and completion | Medium | T328 | FS | 3
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T388 | Paving & Roads - Task 8 | External Development | Prasad | 2027-01-01 | 2027-01-11 | 4 | Open | 1120 | 10 | Kilogram | Paving & Roads - Task 8 execution and completion | High | T355 | SF | 7 | T390,T424,T444
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T389 | Paving & Roads - Task 9 | Electrical | Prasad | 2027-01-01 | 2027-01-03 | 4 | Quantity | 2982 | 10 | Kilogram | Paving & Roads - Task 9 execution and completion | Low | T305 | FS | 7 | T425
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T390 | Paving & Roads - Task 10 | Finishing | Prasad | 2027-01-13 | 2027-01-20 | 4 | Open | 3507 | 10 | Cubic Meter | Paving & Roads - Task 10 execution and completion | Medium | T388 | FS | 2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T391 | Paving & Roads - Task 11 | Architectural Works | Prasad | 2027-01-01 | 2027-01-10 | 4 | Quantity | 321 | 10 | Cubic Meter | Paving & Roads - Task 11 execution and completion | Low | T317 | FS | -2 | T402
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T392 | Paving & Roads - Task 12 | Structural Works | Prasad | 2027-01-01 | 2027-01-04 | 4 | Open | 534 | 10 | Cubic Meter | Paving & Roads - Task 12 execution and completion | Low | T313 | FS | 5 | T426
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T393 | Paving & Roads - Task 13 | Structural Works | Prasad | 2027-01-01 | 2027-01-05 | 4 | Quantity | 3107 | 10 | Numbers | Paving & Roads - Task 13 execution and completion | Low
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T394 | Paving & Roads - Task 14 | External Development | Prasad | 2027-01-01 | 2027-01-11 | 3 | Open | 1337 | 10 | Kilogram | Paving & Roads - Task 14 execution and completion | Medium | T326 | SF | 1 | T402,T420
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T395 | Paving & Roads - Task 15 | Structural Works | Prasad | 2027-01-15 | 2027-01-24 | 3 | Quantity | 1667 | 10 | Kilogram | Paving & Roads - Task 15 execution and completion | Low | T382 | FS | 7 | T439
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T396 | Paving & Roads - Task 16 | Architectural Works | Prasad | 2027-01-01 | 2027-01-09 | 3 | Open | 4858 | 10 | Cubic Meter | Paving & Roads - Task 16 execution and completion | Low |  |  |  | T412
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T397 | Paving & Roads - Task 17 | Electrical | Prasad | 2027-01-01 | 2027-01-03 | 3 | Open | 16 | 10 | Numbers | Paving & Roads - Task 17 execution and completion | Low | T318 | FS | 6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T398 | Paving & Roads - Task 18 | Structural Works | Prasad | 2027-01-01 | 2027-01-09 | 3 | Quantity | 4925 | 10 | Feet | Paving & Roads - Task 18 execution and completion | High | T353 | FS | 4
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T399 | Paving & Roads - Task 19 | Preliminaries & Site Works | Vamsi | 2027-01-01 | 2027-01-08 | 3 | Open | 130 | 10 | Kilogram | Paving & Roads - Task 19 execution and completion | Low | T357 | FS | -2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T400 | Paving & Roads - Task 20 | Finishing | Vamsi | 2027-01-01 | 2027-01-05 | 3 | Quantity | 3556 | 10 | Cubic Meter | Paving & Roads - Task 20 execution and completion | High | T329,T307 | SS,FS | 7,-1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T401 | Paving & Roads - Task 21 | Preliminaries & Site Works | Vamsi | 2027-01-01 | 2027-01-09 | 3 | Open | 4678 | 10 | Cubic Meter | Paving & Roads - Task 21 execution and completion | High | T359 | FF | 3 | T419
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T402 | Paving & Roads - Task 22 | HVAC Systems | Vamsi | 2027-01-17 | 2027-01-21 | 3 | Quantity | 1920 | 10 | Kilogram | Paving & Roads - Task 22 execution and completion | Low | T333,T391,T394 | FS,FS,FS | 1,5,6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T403 | Paving & Roads - Task 23 | HVAC Systems | Vamsi | 2027-01-01 | 2027-01-07 | 3 | Open | 329 | 10 | Square Meter | Paving & Roads - Task 23 execution and completion | Low | T327 | FS | 6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T404 | Paving & Roads - Task 24 | Structural Works | Vamsi | 2027-01-01 | 2027-01-10 | 3 | Quantity | 4966 | 10 | Numbers | Paving & Roads - Task 24 execution and completion | High
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T405 | Paving & Roads - Task 25 | Architectural Works | Vamsi | 2027-01-01 | 2027-01-10 | 3 | Open | 4228 | 10 | Cubic Meter | Paving & Roads - Task 25 execution and completion | High | T322 | FS | 3
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T406 | Paving & Roads - Task 26 | Electrical | Vamsi | 2027-01-01 | 2027-01-09 | 3 | Quantity | 3570 | 10 | Feet | Paving & Roads - Task 26 execution and completion | Medium
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T407 | Paving & Roads - Task 27 | Structural Works | Vamsi | 2027-01-01 | 2027-01-11 | 3 | Open | 2146 | 10 | Numbers | Paving & Roads - Task 27 execution and completion | Medium |  |  |  | T435
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T408 | Paving & Roads - Task 28 | Plumbing & Sanitary | Vamsi | 2027-01-01 | 2027-01-04 | 3 | Open | 1352 | 10 | Kilogram | Paving & Roads - Task 28 execution and completion | Medium | T355 | FS | 4
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Paving & Roads | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T409 | Paving & Roads - Task 29 | Electrical | Vamsi | 2027-01-01 | 2027-01-03 | 3 | Quantity | 826 | 10 | Cubic Meter | Paving & Roads - Task 29 execution and completion | Medium |  |  |  | T425
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T410 | Utilities - Task 1 | Structural Works | Vamsi | 2027-01-01 | 2027-01-10 | 3 | Open | 127 | 10 | Numbers | Utilities - Task 1 execution and completion | High
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T411 | Utilities - Task 2 | Preliminaries & Site Works | Vamsi | 2027-01-09 | 2027-01-17 | 3 | Quantity | 1339 | 10 | Square Meter | Utilities - Task 2 execution and completion | Medium | T372 | FS | 4
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T412 | Utilities - Task 3 | Preliminaries & Site Works | Vamsi | 2027-01-10 | 2027-01-15 | 3 | Open | 1406 | 10 | Kilogram | Utilities - Task 3 execution and completion | Low | T396 | FS | 1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T413 | Utilities - Task 4 | Architectural Works | Vamsi | 2027-01-09 | 2027-01-17 | 3 | Quantity | 558 | 10 | Meter | Utilities - Task 4 execution and completion | Low | T376 | FS | -1 | T422
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T414 | Utilities - Task 5 | Structural Works | Vamsi | 2027-01-01 | 2027-01-03 | 3 | Open | 4934 | 10 | Square Meter | Utilities - Task 5 execution and completion | Medium | T334 | FS | -1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T415 | Utilities - Task 6 | Preliminaries & Site Works | Vamsi | 2027-01-10 | 2027-01-14 | 3 | Quantity | 1215 | 10 | Square Meter | Utilities - Task 6 execution and completion | Low | T383,T350,T384 | FS,FS,FF | 2,2,2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T416 | Utilities - Task 7 | Finishing | Vamsi | 2027-01-01 | 2027-01-11 | 3 | Open | 3126 | 10 | Cubic Meter | Utilities - Task 7 execution and completion | High | T358 | SS | 4 | T443
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T417 | Utilities - Task 8 | Structural Works | Prasad | 2027-01-01 | 2027-01-08 | 3 | Quantity | 1911 | 10 | Cubic Meter | Utilities - Task 8 execution and completion | High | T346 | FS | 2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T418 | Utilities - Task 9 | External Development | Prasad | 2027-01-01 | 2027-01-11 | 3 | Open | 2865 | 10 | Cubic Meter | Utilities - Task 9 execution and completion | Medium | T372 | SF | 1 | T425
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T419 | Utilities - Task 10 | Structural Works | Prasad | 2027-01-08 | 2027-01-14 | 3 | Open | 2224 | 10 | Kilogram | Utilities - Task 10 execution and completion | Low | T401,T341 | FS,FS | -1,1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T420 | Utilities - Task 11 | External Development | Prasad | 2027-01-09 | 2027-01-11 | 3 | Quantity | 2207 | 10 | Numbers | Utilities - Task 11 execution and completion | Low | T394 | FS | -2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T421 | Utilities - Task 12 | Electrical | Prasad | 2027-01-01 | 2027-01-07 | 3 | Open | 1808 | 10 | Kilogram | Utilities - Task 12 execution and completion | High
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T422 | Utilities - Task 13 | HVAC Systems | Prasad | 2027-01-22 | 2027-01-28 | 3 | Quantity | 3995 | 10 | Meter | Utilities - Task 13 execution and completion | High | T413 | FS | 5
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T423 | Utilities - Task 14 | External Development | Prasad | 2027-01-01 | 2027-01-03 | 3 | Open | 2483 | 10 | Square Meter | Utilities - Task 14 execution and completion | Medium | T349,T347 | FS,SF | -1,-1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T424 | Utilities - Task 15 | External Development | Prasad | 2027-01-09 | 2027-01-18 | 3 | Quantity | 2357 | 10 | Numbers | Utilities - Task 15 execution and completion | High | T388 | FS | -2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T425 | Utilities - Task 16 | HVAC Systems | Prasad | 2027-01-16 | 2027-01-24 | 3 | Open | 1116 | 10 | Kilogram | Utilities - Task 16 execution and completion | Medium | T389,T418,T409 | FS,FS,SS | 5,5,3
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T426 | Utilities - Task 17 | Structural Works | Prasad | 2027-01-03 | 2027-01-10 | 3 | Quantity | 2600 | 10 | Feet | Utilities - Task 17 execution and completion | Low | T392 | FS | -1 | T439
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T427 | Utilities - Task 18 | Preliminaries & Site Works | Prasad | 2027-01-01 | 2027-01-11 | 3 | Open | 4199 | 10 | Meter | Utilities - Task 18 execution and completion | Low
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T428 | Utilities - Task 19 | HVAC Systems | Prasad | 2027-01-01 | 2027-01-07 | 3 | Quantity | 4045 | 10 | Kilogram | Utilities - Task 19 execution and completion | Low | T346 | FS | 1
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T429 | Utilities - Task 20 | Architectural Works | Prasad | 2027-01-01 | 2027-01-07 | 3 | Open | 2599 | 10 | Feet | Utilities - Task 20 execution and completion | Medium | T354 | SS | 6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T430 | Utilities - Task 21 | Structural Works | Prasad | 2027-01-01 | 2027-01-05 | 3 | Open | 3633 | 10 | Square Meter | Utilities - Task 21 execution and completion | Low | T357 | FS | -2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T431 | Utilities - Task 22 | External Development | Prasad | 2027-01-01 | 2027-01-07 | 3 | Quantity | 3396 | 10 | Cubic Meter | Utilities - Task 22 execution and completion | Low
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T432 | Utilities - Task 23 | Architectural Works | Prasad | 2027-01-01 | 2027-01-11 | 3 | Open | 3890 | 10 | Meter | Utilities - Task 23 execution and completion | High | T349,T343 | FS,FS | 0,5
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T433 | Utilities - Task 24 | External Development | Prasad | 2027-01-01 | 2027-01-09 | 3 | Quantity | 4155 | 10 | Cubic Meter | Utilities - Task 24 execution and completion | Low
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T434 | Utilities - Task 25 | External Development | Prasad | 2027-01-01 | 2027-01-09 | 3 | Open | 4831 | 10 | Kilogram | Utilities - Task 25 execution and completion | High |  |  |  | T443
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T435 | Utilities - Task 26 | Structural Works | Prasad | 2027-01-11 | 2027-01-16 | 3 | Quantity | 2620 | 10 | Kilogram | Utilities - Task 26 execution and completion | Low | T407 | FS | 0
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T436 | Utilities - Task 27 | HVAC Systems | Prasad | 2027-01-15 | 2027-01-23 | 3 | Open | 2449 | 10 | Square Meter | Utilities - Task 27 execution and completion | Low | T360 | FS | 6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T437 | Utilities - Task 28 | Plumbing & Sanitary | Prasad | 2027-01-01 | 2027-01-11 | 3 | Quantity | 1755 | 10 | Feet | Utilities - Task 28 execution and completion | Medium
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T438 | Utilities - Task 29 | External Development | Prasad | 2027-01-01 | 2027-01-03 | 3 | Open | 4610 | 10 | Kilogram | Utilities - Task 29 execution and completion | Medium | T336 | FS | 6
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T439 | Utilities - Task 30 | Architectural Works | Prasad | 2027-01-17 | 2027-01-21 | 3 | Quantity | 2733 | 10 | Square Meter | Utilities - Task 30 execution and completion | Medium | T395,T426,T370 | SF,FS,FS | 5,4,7
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T440 | Utilities - Task 31 | Structural Works | Prasad | 2027-01-01 | 2027-01-09 | 2 | Open | 3202 | 10 | Numbers | Utilities - Task 31 execution and completion | Medium | T358 | FS | 7
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T441 | Utilities - Task 32 | External Development | Prasad | 2027-01-01 | 2027-01-08 | 2 | Open | 524 | 10 | Numbers | Utilities - Task 32 execution and completion | Medium |  |  |  | T442
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T442 | Utilities - Task 33 | Structural Works | Prasad | 2027-01-06 | 2027-01-13 | 2 | Quantity | 3208 | 10 | Cubic Meter | Utilities - Task 33 execution and completion | Medium | T441 | FS | -2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T443 | Utilities - Task 34 | Finishing | Prasad | 2027-01-01 | 2027-01-09 | 2 | Open | 4252 | 10 | Numbers | Utilities - Task 34 execution and completion | Low | T434,T416 | SS,FF | 0,-2
External Works | Bharath | 2027-01-01 | 2027-04-30 | 10 | Utilities | Mahesh | 2027-01-01 | 2027-04-30 | 30 | T444 | Utilities - Task 35 | Finishing | Prasad | 2027-01-14 | 2027-01-18 | 2 | Quantity | 856 | 10 | Numbers | Utilities - Task 35 execution and completion | Low | T359,T388 | FS,FS | -2,3